## Geotech
RC DRILLING | Hourly / Daily Costs
Geotech Drilling | Rigs Mob/ Demob | L.O.A. (Crew / day) | Metre Drilled | Truck Drill Operating (HR) | Standby (HR) | Air Compressor | Forced Air Heater | Water Line Heater | Support Vehicle | Oil/Gas Kit | Comm Kit | Fuel (+10%) | Daily Costs | Cumulative Daily Costs Cost | De-Icing Fluid | 2" Slotted PVC | 2" Solid PVC | 2" J-Pluig | 2" End Cap | Casing Protector | Fast Set Concrete | Bentonite Chips | Bentonite Pellets | Filter Sand | Daily Tools & Consumables Cost | Cumulative Tools & Consumables Cost | Comments
38925.439 | 2400 | 496 | 0 | 336 | 259 | 604 | 175 | 215 | 310 | 78 | 61 | 1.1 |  |  | 22 | 56.56 | 37.08 | 30.13 | 3.26 | 200.28 | 26.92 | 29.98 | 232.4 | 27.51
2021-01-31 | 1 | [11 empty] | 2400 | 2400 | [10 empty] | 0 | 0
2021-02-01 |  |  |  | 2 | [7 empty] | 170 | 859 | 3259 | [10 empty] | 0 | 0 | Compressor won't start. Travel to FSJ for rental unit
2021-02-02 |  | 1 | 28.5 | 12.75 |  | 1 |  |  | 1 |  | 1 | 94.29 | 5858.719 | 9117.719 | [10 empty] | 0 | 0
2021-02-03 |  | 1 | 20 | 12.5 |  | 1 |  |  | 1 |  | 1 | 252 | 5948.2 | 15065.919 | 2 | [6 empty] | 5 |  |  | 193.9 | 193.9
2021-02-04 |  | 1 | 14 | 10 | 2 | 1 |  |  | 1 |  | 1 | 278 | 5654.8 | 20720.719 | 4 | 4 | 3 |  | 4 | 2 |  | 3 |  | 8 | 1149.1 | 1343
2021-02-05 |  | 1 | 2.44 | 3.5 | 8.5 | 1 |  |  | 1 |  | 1 | 164 | 5028.9 | 25749.619 | [7 empty] | 1 |  |  | 29.98 | 1372.98
2021-02-06 |  | 1 | 24.08 | 13.5 |  | 1 |  |  | 1 |  | 1 |  | 6007 | 31756.619 | 2 | [6 empty] | 2 |  |  | 103.96 | 1476.94
2021-02-07 |  | 1 |  | 4 |  | 1 |  |  | 1 |  | 1 | 270 | 3112 | 34868.619 | [7 empty] | 6 |  |  | 179.88 | 1656.82 | Can't get rental compressor going, Kim cancels final hole, Geotech starts demobe
2021-02-08 | 1 | [11 empty] | 2400 | 37268.619 | [10 empty] | 0 | 1656.82
2021-02-09 | [12 empty] | 0 | 37268.619 | [10 empty] | 0 | 1656.82
2021-02-10 | [12 empty] | 0 | 37268.619 | [10 empty] | 0 | 1656.82
| 2 | 6 | 89.02 | 58.25 | 10.5 | 6 | 0 | 0 | 6 | 0 | 6 | 1228.29 | 37268.619 |  | 8 | 4 | 3 | 0 | 4 | 2 | 0 | 17 | 0 | 8 | 1656.82

## Ecofor
ECOFOR | Project Management (Hr) | Enviro Monitor (Field / Hr) | QP (Field / Hr) | Enviro Tech (Field / Hr) | QP (Office / Hr) | YSI & Calibration Kit (Day) | Truck Rental (day) | L.O.A. | Accomodations | Daily | Cumulative | Comments
13637.5 | 135 | 85 | 115 | 75 | 115 | 50 | 150 | 50 | 125 | Cost | Cost
2021-01-31 |  | 4.5 | 3 |  |  |  | 2 | 2 | 2 | 1377.5 | 1377.5
2021-02-01 |  | 11 | 12 |  |  | 1 | 2 | 2 | 1 | 2890 | 4267.5
2021-02-02 |  | 12 |  |  | 9 | 1 | 1 | 1 | 1 | 2430 | 6697.5
2021-02-03 |  | 12 |  |  | 1 | 1 | 1 | 1 | 1 | 1510 | 8207.5
2021-02-04 |  | 10 |  |  | 1 | 1 | 1 | 1 | 1 | 1340 | 9547.5
2021-02-05 |  | 13 |  |  | 1 | 1 | 1 | 1 | 1 | 1595 | 11142.5
2021-02-06 |  | 13 |  |  |  | 1 | 1 | 1 | 1 | 1480 | 12622.5
2021-02-07 |  | 9 |  |  |  | 1 | 1 | 1 |  | 1015 | 13637.5 | Final hole BH20-08 cancelled, Jessica departs site
2021-02-08 | [9 empty] | 0 | 13637.5
2021-02-09 | [9 empty] | 0 | 13637.5
2021-02-10 | [9 empty] | 0 | 13637.5
13637.5
"Day Rate" based on 10 hour day
$850/day = $85/hour
$1150/day=$115/hr
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4hr on site, 5hr charge to demobe to FSJ from Hermann.

## Wood
WOOD | Geotech Field (Hr) | Lab Testing | Truck (day) | L.O.A. | Accomodations | Daily | Cumulative | Comments
12023 | 119 | 1000 | 200 | 80 | 150 | Cost | Cost
2021-01-31 | [5 empty] | 0 | 0
2021-02-01 | 8 |  | 1 | 1 | 1 | 1382 | 1382
2021-02-02 | 12.5 |  | 1 | 1 | 1 | 1917.5 | 3299.5
2021-02-03 | 12.5 |  | 1 | 1 | 1 | 1917.5 | 5217
2021-02-04 | 11 |  | 1 | 1 | 1 | 1739 | 6956 | Vehicle incident, failed drug test, conference call
2021-02-05 | 9 |  | 1 | 1 | 1 | 1501 | 8457 | Kim Sinclair mobing to site; 5.5hr travel, time on site and drive to Tumbler 3.5hr
2021-02-06 | 13 |  | 1 | 1 | 1 | 1977 | 10434
2021-02-07 | 11 |  | 1 | 1 |  | 1589 | 12023 | Final hole BH20-08 cancelled, Kim departs site for PG (5.5hrs)
2021-02-08 | [5 empty] | 0 | 12023
2021-02-09 | [5 empty] | 0 | 12023
2021-02-10 | [5 empty] | 0 | 12023
12023
Note on B10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5.5hrs on site, 5.5hr demob to PG

## Piteau
| Technical / Secretarial | [5 empty] | Direct Costs
Piteau | Principal Geotech Engineer (Hogarth) | Senior Geotech Engineer (Office) (Rosted) | Junior Geotech, Engineer (Savage) | Junior Geotech, Engineer (McFadden) | ACAD | Admin & Document Support | Truck Rental (day) | Fuel | Airfare | Transit Vehicle | Accomodations & Meals | Radio | Misc. Expenses | 7.5% Admin Fee | Daily | Cumulative | Comments | Invoice Sub-Total | GST | Total Invoice
88429.291 | 272.5 | 231.75 | 137.5 | 137.5 | 145 | 117.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Cost | Cost
2021-01-05 | [14 empty] | 0 | 0
2021-01-06 | [14 empty] | 0 | 0
2021-01-07 | [14 empty] | 0 | 0
2021-01-08 | [14 empty] | 0 | 0
2021-01-09 | [14 empty] | 0 | 0
2021-01-10 | [14 empty] | 0 | 0
2021-01-11 | [14 empty] | 0 | 0
2021-01-12 | [14 empty] | 0 | 0
2021-01-13 | [14 empty] | 0 | 0
2021-01-14 | [14 empty] | 0 | 0
2021-01-15 | [14 empty] | 0 | 0
2021-01-16 | [14 empty] | 0 | 0
2021-01-17 | [14 empty] | 0 | 0
2021-01-18 | 14.25 | [13 empty] | 3883.125 | 3883.125 | Marianne 17.5 hrs removed, Haegert 3.5hrs removed
2021-01-19 |  | 15.25 | 21 | [11 empty] | 6421.6875 | 10304.8125 | Jake hrs reduced by 6
2021-01-20 | [8 empty] | 1105 | [5 empty] | 1105 | 11409.8125
2021-01-21 |  | 8 | 8 | [5 empty] | 858.43 | [5 empty] | 3812.43 | 15222.2425 | Marianne and Jake mob to site
2021-01-22 |  | 10 | 10 | [5 empty] | 650.25 | [5 empty] | 4342.75 | 19564.9925
2021-01-23 |  | 5 | 12 | [11 empty] | 2808.75 | 22373.7425
2021-01-24 |  | 13.5 | 13.5 | [11 empty] | 4984.875 | 27358.6175
2021-01-25 |  | 13 | 13 | 5.5 | [10 empty] | 5556.5 | 32915.1175 | Riley hrs reduced by 4.5
2021-01-26 |  | 5.5 | 12 | [11 empty] | 2924.625 | 35839.7425 | Marianne at Wolverine most of day
2021-01-27 |  |  | 12 | [11 empty] | 1650 | 37489.7425
2021-01-28 |  | 12 | 12 | [11 empty] | 4431 | 41920.7425
2021-01-29 |  | 8 | 12 | [11 empty] | 3504 | 45424.7425 | Marianne departs
2021-01-30 |  |  | 12 | [11 empty] | 1650 | 47074.7425
2021-01-31 |  |  | 12 |  |  |  | 921.3 | [6 empty] | 265.1235 | 2836.4235 | 49911.166 |  | 49911.166 | 2495.5583 | 52406.7243
2021-02-01 |  |  | 12 | [11 empty] | 1650 | 51561.166
2021-02-02 |  |  | 12 | [11 empty] | 1650 | 53211.166
2021-02-03 |  |  | 12 | [11 empty] | 1650 | 54861.166
2021-02-04 |  |  | 12 | [11 empty] | 1650 | 56511.166
2021-02-05 | 2.5 |  | 12 | 12 | [10 empty] | 3981.25 | 60492.416 | Riley McFadden arrives
2021-02-06 |  |  | 12 | 12 | [10 empty] | 3300 | 63792.416
2021-02-07 | 12 |  |  | 12 | [10 empty] | 4920 | 68712.416 | Jake Savage departs, James Hogarth on site with Riley
2021-02-08 | 1.25 |  |  | 12 | [10 empty] | 1990.625 | 70703.041
2021-02-09 | 4.5 |  |  | 12 | [10 empty] | 2876.25 | 73579.291
2021-02-10 |  |  |  | 12 | [10 empty] | 1650 | 75229.291
2021-02-11 |  |  |  | 12 | [10 empty] | 1650 | 76879.291
2021-02-12 |  |  |  | 12 | [10 empty] | 1650 | 78529.291
2021-02-13 |  |  |  | 12 | [10 empty] | 1650 | 80179.291
2021-02-14 |  |  |  | 12 | [10 empty] | 1650 | 81829.291
2021-02-15 |  |  |  | 12 | [10 empty] | 1650 | 83479.291
2021-02-16 |  |  |  | 12 | [10 empty] | 1650 | 85129.291
2021-02-17 |  |  |  | 12 | [10 empty] | 1650 | 86779.291
2021-02-18 |  |  |  | 12 | [10 empty] | 1650 | 88429.291 | Riley Departs
2021-02-19 | [14 empty] | 0 | 88429.291
2021-02-20 | [14 empty] | 0 | 88429.291
2021-02-21 | [14 empty] | 0 | 88429.291
2021-02-22 | [14 empty] | 0 | 88429.291
2021-02-23 | [14 empty] | 0 | 88429.291
2021-02-24 | [14 empty] | 0 | 88429.291
2021-02-25 | [14 empty] | 0 | 88429.291
2021-02-26 | [14 empty] | 0 | 88429.291
2021-02-27 | [14 empty] | 0 | 88429.291
88429.291
[7 empty] | 3100 | 1250 | 3 | 300 | 9100 | 150 | 1476.88
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Office hrs worked prior to mob. No breakdown supplied as requested

## Century
CENTURY WIRELINE | Rates | [12 empty] | Additional Charges | [7 empty] | Totals |  | Comments | Subtotal | GST | Subtotal
| Daily Rate | Daily Rate (on call) | Mobilization Rate (day) | Overtime Rate (hr) | Dip Survey | Sonic Survey | Xtra | Supervisor Shift Change (day) | ATV Televiewer (m) | OTV Televiewer (m) | Well CAD Conversion (/well) | Daily | Cumulative | TIFF / LAS Files | TIFF / LAS Files (Extra Sets) | Fuel Charge (day) | Per Diem (day/man) | Min Charge (m) | Accomodation Rate (day/man) | Daily | Cumulative | Daily | Cumulative
73392.26 | 2850 | 1800 | 2500 | 325 | 300 | 200 | 300 | 1500 | 6 | 8 | 400 | Cost | Cost | 50 | 40 | 100 | 65 | 1 | 165 | Cost | Cost | Total | Total
2021-01-21 | [11 empty] | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
2021-01-22 |  |  | 1 | [8 empty] | 2500 | 2500 |  |  |  | 1 |  | 1 | 230 | 230 | 2730 | 2730
2021-01-23 |  | 1 | [9 empty] | 1800 | 4300 |  |  |  | 1 |  | 1 | 230 | 460 | 2030 | 4760
2021-01-24 |  | 1 | [9 empty] | 1800 | 6100 |  |  |  | 1 |  | 1 | 230 | 690 | 2030 | 6790
2021-01-25 | 1 |  |  |  | 1 |  |  |  | 31 |  |  | 3336 | 9436 | 1 |  | 1 | 1 | 294 | 1 | 674 | 1364 | 4010 | 10800
2021-01-26 | 1 |  |  |  | 1 |  |  |  | 42 |  |  | 3402 | 12838 | 1 |  | 1 | 1 | 228 | 1 | 608 | 1972 | 4010 | 14810
2021-01-27 |  | 1 | [9 empty] | 1800 | 14638 |  |  |  | 1 |  | 1 | 230 | 2202 | 2030 | 16840
2021-01-28 |  | 1 | [9 empty] | 1800 | 16438 |  |  |  | 1 |  | 1 | 230 | 2432 | 2030 | 18870
2021-01-29 | 1 |  |  |  | 1 |  |  |  | 85 |  |  | 3660 | 20098 | 1 |  | 1 | 1 |  | 1 | 380 | 2812 | 4040 | 22910
2021-01-30 | [11 empty] | 0 | 20098 | [6 empty] | 0 | 2812 | 0 | 22910 | Brule Logging
2021-01-31 |  | 1 | [9 empty] | 1800 | 21898 |  |  |  | 1 |  | 1 | 230 | 3042 | 2030 | 24940
2021-02-01 |  | 1 | [9 empty] | 1800 | 23698 |  |  |  | 1 |  | 1 | 230 | 3272 | 2030 | 26970
2021-02-02 | 1 |  |  |  | 1 |  |  |  | 153 |  |  | 4068 | 27766 | 1 |  | 1 | 1 |  | 1 | 380 | 3652 | 4448 | 31418
2021-02-03 | [11 empty] | 0 | 27766 | [6 empty] | 0 | 3652 | 0 | 31418 | Brule Logging
2021-02-04 |  | 1 | [9 empty] | 1800 | 29566 |  |  |  | 1 |  | 1 | 230 | 3882 | 2030 | 33448
2021-02-05 |  | 1 | [5 empty] | 1 |  |  |  | 3300 | 32866 |  |  |  | 2 |  | 2 | 460 | 4342 | 3760 | 37208 | Rylan out, Barkley in
2021-02-06 | 1 |  |  |  | 1 |  |  |  | 23.04 |  |  | 3288.24 | 36154.24 | 1 |  | 1 | 1 | 341.76 | 1 | 721.76 | 5063.76 | 4010 | 41218
2021-02-07 |  | 1 | [9 empty] | 1800 | 37954.24 |  |  |  | 1 |  | 1 | 230 | 5293.76 | 2030 | 43248
2021-02-08 | 1 |  |  |  | 1 |  |  |  | 45.22 |  |  | 3421.32 | 41375.56 | 1 |  | 1 | 1 | 208.68 | 1 | 588.68 | 5882.44 | 4010 | 47258
2021-02-09 |  | 1 | [9 empty] | 1800 | 43175.56 |  |  |  | 1 |  | 1 | 230 | 6112.44 | 2030 | 49288
2021-02-10 |  | 1 | [9 empty] | 1800 | 44975.56 |  |  |  | 1 |  | 1 | 230 | 6342.44 | 2030 | 51318
2021-02-11 |  | 1 | [9 empty] | 1800 | 46775.56 |  |  |  | 1 |  | 1 | 230 | 6572.44 | 2030 | 53348
2021-02-12 | 1 |  |  |  | 1 |  |  |  | 66.98 |  |  | 3551.88 | 50327.44 | 1 |  | 1 | 1 |  | 1 | 380 | 6952.44 | 3931.88 | 57279.88
2021-02-13 |  | 1 | [9 empty] | 1800 | 52127.44 |  |  |  | 1 |  | 1 | 230 | 7182.44 | 2030 | 59309.88
2021-02-14 |  | 1 | [9 empty] | 1800 | 53927.44 |  |  |  | 1 |  | 1 | 230 | 7412.44 | 2030 | 61339.88
2021-02-15 | 1 |  |  |  | 1 |  |  |  | 73.73 |  |  | 3592.38 | 57519.82 | 1 |  | 1 | 1 |  | 1 | 380 | 7792.44 | 3972.38 | 65312.26
2021-02-16 |  | 1 | [9 empty] | 1800 | 59319.82 |  |  |  | 1 |  | 1 | 230 | 8022.44 | 2030 | 67342.26
2021-02-17 | 1 | [10 empty] | 2850 | 62169.82 | 1 | 8 | 1 | 1 |  | 1 | 700 | 8722.44 | 3550 | 70892.26
2021-02-18 |  |  | 1 | [8 empty] | 2500 | 64669.82 | [6 empty] | 0 | 8722.44 | 2500 | 73392.26
2021-02-19 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-02-20 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-02-21 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-02-22 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-02-23 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-02-24 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-02-25 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-02-26 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-02-27 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-02-28 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-01 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-02 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-03 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-04 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-05 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-06 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-07 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-08 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-09 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-10 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-11 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-12 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-13 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-14 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-15 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-16 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-17 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-18 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-19 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-20 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-21 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-22 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-23 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-24 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-25 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-26 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-27 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-28 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-29 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-30 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
2021-03-31 | [11 empty] | 0 | 64669.82 | [6 empty] | 0 | 8722.44 | 0 | 73392.26
[12 empty] | 64669.82 | [7 empty] | 8722.44 |  | 73392.26
Note on J16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 153m actual logged (from 41m to 194m)

## 4Evergreen
4Evergreen Resources | [19 empty] | TOTAL DAILY COST | James' Daily Breakdown
|  | EMT Services | Cat 336 (Unit #102) | Dozer- D7 (hr) | Tandem Dump Truck (hr) | Tandem cost plus (10%) | Tridrive Dump Truck (hr) | Tridrive cost plus (10%) | Truck (day) | Daily Costs | Cumulative Costs | Travel Time (hr/man) | Operator Time (hr/man) | Subsistence (day/man) | Supervisor (day) | FUEL (Cost Plus) | Overtime | Hourly / Daily Costs | Cumulative Hourly Costs |  | Labour | Conuma's dozer time | 336 Excavator time | Wheel Loader | Travel
154552.5 |  | 1105 | 215 | 200 | 160 |  | 175 |  | 200 |  |  | 60 | 65 | 125 | 600 |  | 90 |  |  |  | (Hr) | (Hr) | (Hr) | (Hr) | (Hr)
2021-01-20 | Day | 1 | 10 | [5 empty] | 1 | 3455 | 3455 | 1 |  | 2 |  |  |  | 310 | 310 | 3765 | 4.5 |  | 5.5 | 1
| Night | [8 empty] | 0 | 3455 | [6 empty] | 0 | 310 | 0
2021-01-21 | Day | 1 | 12 | [5 empty] | 1 | 3885 | 7340 | 1 |  | 1 |  |  |  | 185 | 495 | 4070 | 2.5 | 5 | 4 | 1 | 2.5
| Night | [8 empty] | 0 | 7340 | [6 empty] | 0 | 495 | 0
2021-01-22 | Day | 1 | 12 | [5 empty] | 1 | 3885 | 11225 | 1 |  | 2 |  |  |  | 310 | 805 | 4195 | 3.5 |  | 8 | 1
| Night | 660 | [6 empty] | 1 | 860 | 12085 | 1 | [5 empty] | 60 | 865 | 920
2021-01-23 | Day | 1 | 12 | [5 empty] | 1 | 3885 | 15970 | 1 |  | 2 |  |  |  | 310 | 1175 | 4195 | 1 | 8 | 3 | 1 | 1
| Night | 1 | [7 empty] | 1105 | 17075 |  |  | 1 |  |  |  | 125 | 1300 | 1230
2021-01-24 | Day | 1 | 7 | [5 empty] | 1 | 2810 | 19885 | 1 |  | 2 |  |  |  | 310 | 1610 | 3120 |  | 6 | 1.5 | 1
| Night | 1 | [7 empty] | 1105 | 20990 |  |  | 1 |  |  |  | 125 | 1735 | 1230
2021-01-25 | Day | 1 | 12 | [5 empty] | 1 | 3885 | 24875 | 1 |  | 2 |  |  |  | 310 | 2045 | 4195 | 1 |  | 11 | 1 | 1
| Night | 1 | [7 empty] | 1105 | 25980 |  |  | 1 |  |  |  | 125 | 2170 | 1230
2021-01-26 | Day | 1 | 7.5 | [5 empty] | 1 | 2917.5 | 28897.5 | 1 |  | 2 |  |  |  | 310 | 2480 | 3227.5 | 0.5 |  | 6 | 2 | 0.5 | no work done until 1130 due to Finning visit
| Night | 1 | [7 empty] | 1105 | 30002.5 |  |  | 1 |  |  |  | 125 | 2605 | 1230
2021-01-27 | Day | 1 | 12 | [5 empty] | 1 | 3885 | 33887.5 | 1 |  | 2 |  |  |  | 310 | 2915 | 4195 |  |  | 12 | 1
| Night | 1 | [7 empty] | 1105 | 34992.5 |  |  | 1 |  |  |  | 125 | 3040 | 1230
2021-01-28 | Day | 1 | 12 | [5 empty] | 1 | 3885 | 38877.5 | 1 |  | 2 |  |  |  | 310 | 3350 | 4195 | 10 |  | 2 | 1
| Night | 1 | [7 empty] | 1105 | 39982.5 |  |  | 1 |  |  |  | 125 | 3475 | 1230
2021-01-29 | Day | 1 | 12 | [5 empty] | 1 | 3885 | 43867.5 | 1 |  | 2 |  |  |  | 310 | 3785 | 4195 | 8 | 2 | 2 | 1
| Night | 1 | [7 empty] | 1105 | 44972.5 |  |  | 1 |  |  |  | 125 | 3910 | 1230
2021-01-30 | Day | 1 | 12 | [5 empty] | 1 | 3885 | 48857.5 | 1 |  | 2 |  |  |  | 310 | 4220 | 4195 |  |  | 3 | 1 | 9 | last day James on site, 4Evergreen notified regarding excavator demobe.
| Night | 1 | [7 empty] | 1105 | 49962.5 |  |  | 1 |  |  |  | 125 | 4345 | 1230
2021-01-31 | Day | 1 | [7 empty] | 1105 | 51067.5 |  |  | 1 |  |  |  | 125 | 4470 | 1230
| Night | 1 | [7 empty] | 1105 | 52172.5 |  |  | 1 |  |  |  | 125 | 4595 | 1230
2021-02-01 | Day | 1 | [7 empty] | 1105 | 53277.5 |  |  | 1 |  |  |  | 125 | 4720 | 1230
| Night | 1 | [7 empty] | 1105 | 54382.5 |  |  | 1 |  |  |  | 125 | 4845 | 1230
2021-02-02 | Day | 1 | [7 empty] | 1105 | 55487.5 |  |  | 1 |  |  |  | 125 | 4970 | 1230
| Night | 1 | [7 empty] | 1105 | 56592.5 |  |  | 1 |  |  |  | 125 | 5095 | 1230
2021-02-03 | Day | 1 | [7 empty] | 1105 | 57697.5 |  |  | 1 |  |  |  | 125 | 5220 | 1230
| Night | 1 | [7 empty] | 1105 | 58802.5 |  |  | 1 |  |  |  | 125 | 5345 | 1230
2021-02-04 | Day | 1 | [7 empty] | 1105 | 59907.5 |  |  | 1 |  |  |  | 125 | 5470 | 1230
| Night | 1 | [7 empty] | 1105 | 61012.5 |  |  | 1 |  |  |  | 125 | 5595 | 1230
2021-02-05 | Day | 1 | [7 empty] | 1105 | 62117.5 |  |  | 1 |  |  |  | 125 | 5720 | 1230
| Night | 1 | [7 empty] | 1105 | 63222.5 |  |  | 1 |  |  |  | 125 | 5845 | 1230
2021-02-06 | Day | 1 | [7 empty] | 1105 | 64327.5 |  |  | 1 |  |  |  | 125 | 5970 | 1230
| Night | 1 | [7 empty] | 1105 | 65432.5 |  |  | 1 |  |  |  | 125 | 6095 | 1230
2021-02-07 | Day | 1 | [7 empty] | 1105 | 66537.5 |  |  | 1 |  |  |  | 125 | 6220 | 1230
| Night | 1 | [7 empty] | 1105 | 67642.5 |  |  | 1 |  |  |  | 125 | 6345 | 1230
2021-02-08 | Day | 1 | [7 empty] | 1105 | 68747.5 |  |  | 1 |  |  |  | 125 | 6470 | 1230
| Night | 1 | [7 empty] | 1105 | 69852.5 |  |  | 1 |  |  |  | 125 | 6595 | 1230
2021-02-09 | Day | 1 | [7 empty] | 1105 | 70957.5 |  |  | 1 |  |  |  | 125 | 6720 | 1230
| Night | 1 | [7 empty] | 1105 | 72062.5 |  |  | 1 |  |  |  | 125 | 6845 | 1230
2021-02-10 | Day | 1 | [7 empty] | 1105 | 73167.5 |  |  | 1 |  |  |  | 125 | 6970 | 1230
| Night | 1 | [7 empty] | 1105 | 74272.5 |  |  | 1 |  |  |  | 125 | 7095 | 1230
2021-02-11 | Day | 1 | [7 empty] | 1105 | 75377.5 |  |  | 1 |  |  |  | 125 | 7220 | 1230
| Night | 1 | [7 empty] | 1105 | 76482.5 |  |  | 1 |  |  |  | 125 | 7345 | 1230
2021-02-12 | Day | 1 | [7 empty] | 1105 | 77587.5 |  |  | 1 |  |  |  | 125 | 7470 | 1230
| Night | 1 | [7 empty] | 1105 | 78692.5 |  |  | 1 |  |  |  | 125 | 7595 | 1230
2021-02-13 | Day | 1 | [7 empty] | 1105 | 79797.5 |  |  | 1 |  |  |  | 125 | 7720 | 1230
| Night | 1 | [7 empty] | 1105 | 80902.5 |  |  | 1 |  |  |  | 125 | 7845 | 1230
2021-02-14 | Day | 1 | [7 empty] | 1105 | 82007.5 |  |  | 1 |  |  |  | 125 | 7970 | 1230
| Night | 1 | [7 empty] | 1105 | 83112.5 |  |  | 1 |  |  |  | 125 | 8095 | 1230
2021-02-15 | Day | 1 | [7 empty] | 1105 | 84217.5 |  |  | 1 |  |  |  | 125 | 8220 | 1230
| Night | 1 | [7 empty] | 1105 | 85322.5 |  |  | 1 |  |  |  | 125 | 8345 | 1230
2021-02-16 | Day | 1 | [7 empty] | 1105 | 86427.5 |  |  | 1 |  |  |  | 125 | 8470 | 1230
| Night | 1 | [7 empty] | 1105 | 87532.5 |  |  | 1 |  |  |  | 125 | 8595 | 1230
2021-02-17 | Day | 1 | [7 empty] | 1105 | 88637.5 |  |  | 1 |  |  |  | 125 | 8720 | 1230
| Night | 1 | [7 empty] | 1105 | 89742.5 |  |  | 1 |  |  |  | 125 | 8845 | 1230
2021-02-18 | Day | 1 | [7 empty] | 1105 | 90847.5 |  |  | 1 |  |  |  | 125 | 8970 | 1230
| Night | 1 | [7 empty] | 1105 | 91952.5 |  |  | 1 |  |  |  | 125 | 9095 | 1230
2021-02-19 | Day | 1 | [7 empty] | 1105 | 93057.5 |  |  | 1 |  |  |  | 125 | 9220 | 1230
| Night | 1 | [7 empty] | 1105 | 94162.5 |  |  | 1 |  |  |  | 125 | 9345 | 1230
2021-02-20 | Day | 1 | [7 empty] | 1105 | 95267.5 |  |  | 1 |  |  |  | 125 | 9470 | 1230
| Night | 1 | [7 empty] | 1105 | 96372.5 |  |  | 1 |  |  | 5 | 575 | 10045 | 1680
2021-02-21 | Day | 1 | [7 empty] | 1105 | 97477.5 |  |  | 1 |  |  |  | 125 | 10170 | 1230
| Night | [8 empty] | 0 | 97477.5 | [6 empty] | 0 | 10170 | 0
2021-02-22 | Day | 1 | [7 empty] | 1105 | 98582.5 |  |  | 1 |  |  |  | 125 | 10295 | 1230
| Night | 1 | [6 empty] | 1 | 1305 | 99887.5 |  | 12 | 2 |  |  |  | 1030 | 11325 | 2335
2021-02-23 | Day | 1 | [7 empty] | 1105 | 100992.5 |  |  | 1 |  |  |  | 125 | 11450 | 1230
| Night | 1 | [6 empty] | 1 | 1305 | 102297.5 |  | 12 | 2 |  |  |  | 1030 | 12480 | 2335
2021-02-24 | Day | 1 | [7 empty] | 1105 | 103402.5 |  |  | 1 |  |  |  | 125 | 12605 | 1230
| Night | 1 | [6 empty] | 1 | 1305 | 104707.5 |  | 12 | 2 |  |  |  | 1030 | 13635 | 2335
2021-02-25 | Day | 1 | [7 empty] | 1105 | 105812.5 |  |  | 1 |  |  |  | 125 | 13760 | 1230
| Night | 1 | [6 empty] | 1 | 1305 | 107117.5 |  | 12 | 2 |  |  |  | 1030 | 14790 | 2335
2021-02-26 | Day | 1 | [7 empty] | 1105 | 108222.5 |  |  | 1 |  |  |  | 125 | 14915 | 1230
| Night | 1 | [6 empty] | 1 | 1305 | 109527.5 |  | 12 | 2 |  |  |  | 1030 | 15945 | 2335
2021-02-27 | Day | 1 | [7 empty] | 1105 | 110632.5 |  |  | 1 |  |  |  | 125 | 16070 | 1230
| Night | 1 | [6 empty] | 1 | 1305 | 111937.5 |  | 15 | 2 |  |  |  | 1225 | 17295 | 2530
2021-02-28 | Day | 1 | [7 empty] | 1105 | 113042.5 |  |  | 1 |  |  |  | 125 | 17420 | 1230
| Night | 1 | [6 empty] | 1 | 1305 | 114347.5 |  | 12 | 2 |  |  |  | 1030 | 18450 | 2335
2021-03-01 | Day | 1 | [7 empty] | 1105 | 115452.5 |  |  | 1 |  |  |  | 125 | 18575 | 1230
| Night | 1 | [6 empty] | 1 | 1305 | 116757.5 |  | 12 | 2 |  |  |  | 1030 | 19605 | 2335
2021-03-02 | Day | 1 | [7 empty] | 1105 | 117862.5 |  |  | 1 |  |  |  | 125 | 19730 | 1230
| Night | 1 | [6 empty] | 1 | 1305 | 119167.5 | 1 | 12 | 2 |  | 750L |  | 1090 | 20820 | 2395
2021-03-03 | Day | 1 | [7 empty] | 1105 | 120272.5 |  |  | 1 |  |  |  | 125 | 20945 | 1230
| Night | 1 | [6 empty] | 1 | 1305 | 121577.5 | 1 | 12 | 2 |  | 375L |  | 1090 | 22035 | 2395
2021-03-04 | Day | 1 | [7 empty] | 1105 | 122682.5 |  |  | 1 |  |  |  | 125 | 22160 | 1230
| Night | 1 | [6 empty] | 1 | 1305 | 123987.5 | 1 | 12 | 2 |  |  |  | 1090 | 23250 | 2395
2021-03-05 | Day | 1 | [7 empty] | 1105 | 125092.5 |  |  | 1 |  |  |  | 125 | 23375 | 1230
| Night | 1 | [6 empty] | 1 | 1305 | 126397.5 | 1 | 12 | 2 |  | 375 |  | 1090 | 24465 | 2395
2021-03-06 | Day | 1 | [7 empty] | 1105 | 127502.5 |  |  | 1 |  |  |  | 125 | 24590 | 1230
| Night | [8 empty] | 0 | 127502.5 | [6 empty] | 0 | 24590 | 0
2021-03-07 | Day | 1 | [7 empty] | 1105 | 128607.5 |  |  | 1 |  |  |  | 125 | 24715 | 1230
| Night | [8 empty] | 0 | 128607.5 | [6 empty] | 0 | 24715 | 0
2021-03-08 | Day | 1 | [7 empty] | 1105 | 129712.5 |  |  | 1 |  |  |  | 125 | 24840 | 1230
| Night | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
2021-03-09 | Day | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
| Night | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
2021-03-10 | Day | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
| Night | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
2021-03-11 | Day | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
| Night | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
2021-03-12 | Day | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
| Night | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
2021-03-13 | Day | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
| Night | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
2021-03-14 | Day | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
| Night | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
2021-03-15 | Day | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
| Night | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
2021-03-16 | Day | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
| Night | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
2021-03-17 | Day | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
| Night | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
2021-03-18 | Day | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
| Night | [8 empty] | 0 | 129712.5 | [6 empty] | 0 | 24840 | 0
[10 empty] | 129712.5 | [7 empty] | 24840 |  | 154552.5
Note on G37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3 loads due to orientation
Note on G38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3 loads
Note on G39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4 loads
Note on G40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4 loads

## Good Earth
RC DRILLING |  | Hourly / Daily Costs
Good Earth Drilling | Shift | Rigs Mob/ Demob | L.O.A. (/man day) | Total Mob/Demob Costs | Cumulative Mob/Demob Costs | Casing/ Coring Total | Coring 3" (m) | Coring 6" (m) | Hammer 6" (m) | RC 5.75" (m) | Total | Daily Drilling Cost | Cumulative Drilling Cost | Standby Rate (hr) (mainly safety) | Moving / Setup (hr) | Logging (hr) | VWP Installation (hr) | Casing install / removal (hr) | Tripping/ Reaming (hr) | 8 5/8" Core,trip,ream,hammer (hr) | Daily Operating Cost | Cumulative Operating Cost | Forklift (day) | Water Truck (day) | Light Tower / Generator (day) | Core Shack (day) | Daily Ancillary Equipment Cost | Cumulative Ancillary Equipment Cost | 7" Casing (m) | 10 3/4" Casing (m) | 12 3/4" Casing (m) | 7" Casing Shoe | 10 3/4" Casing Shoe | 12 3/4" Casing Shoe | Bit retip | 5 3/4" Hammer Bit | 10 3/4" Hammer Bit | 3" Core Box | 6" Core Box | Polymer | Torqueless | Drill Foam | Flowing hole bladder | Bladder PVC (m) | Hole Plug Cement | Glue/Primer (per) | PVC 1.25" nipple / 90 elbow | PVC 1.25" Valve (per) | Cement bags (paid) | Benny (paid) | Tremmie Line (m) (paid) | P & D | Misc. Product Costs | Conuma seacan cement bags | Comments | Daily Tools & Consumables Cost | Cumulative Tools & Consumables Cost | Cumulative Daily | Total Mob/Demob/L.O.A. Costs | Daily Drilling Cost | Daily Operating Cost | Daily Ancillary Equipment Cost | Daily Tools & Consumables Cost | Total Weekly Invoice | GST (5%) | TOTAL INVOICE | Good Earth Total
665900.31 |  | 7500 | 140 |  |  | n.a. | 185 | 370 | 175 | 70 | (M) | (m) cost | (m) cost | 325 | 325 | 325 | 450 | 550 | 550 | 715 |  |  | 150 | 500 | 100 | 200 |  |  | 55 | 160 | 88 | 300 | 66 | 500 | 1 | 540 | 4200 | 30 | 45 | 190 | 150 | 160 | 865 | 8.5 | 26.39 | 12.5 | 5 | 18 |  |  |  | 1 | 1
2021-01-21 | DS | 1 | 10 | 8900 | 8900 | [5 empty] | 0 | 0 | 0 | [7 empty] | 0 | 0 |  |  |  |  | 0 | 0 | [27 empty] | 0 | 0 | 8900
| NS |  |  | 0 | 8900 | [5 empty] | 0 | 0 | 0 | [7 empty] | 0 | 0 |  |  |  |  | 0 | 0 | [27 empty] | 0 | 0 | 0
2021-01-22 | DS |  | 10 | 1400 | 10300 | [5 empty] | 0 | 0 | 0 | 1.5 | 9.5 | [5 empty] | 3575 | 3575 | 1 | 1 | 1 | 1 | 950 | 950 | [27 empty] | 0 | 0 | 5925
| NS |  |  | 0 | 10300 | [5 empty] | 0 | 0 | 0 | [7 empty] | 0 | 3575 |  |  |  |  | 0 | 950 | [27 empty] | 0 | 0 | 0
2021-01-23 | DS |  | 5 | 700 | 11000 | [5 empty] | 0 | 0 | 0 | 0.5 | [6 empty] | 162.5 | 3737.5 | 1 | 1 | 1 | 1 | 950 | 1900 | [27 empty] | 0 | 0 | 1812.5
| NS |  | 4 | 560 | 11560 | 24 |  |  |  |  | 24 | 0 | 0 | 0.5 |  |  |  | 7.5 |  |  | 4287.5 | 8025 |  |  |  |  | 0 | 1900 | 24 |  |  | 1 | [23 empty] | 1620 | 1620 | 6467.5
2021-01-24 | DS |  | 5 | 700 | 12260 |  | 17.1 |  |  |  | 17.1 | 3163.5 | 3163.5 | 2.5 |  |  |  |  | 1.5 |  | 1637.5 | 9662.5 | 1 | 1 | 1 | 1 | 950 | 2850 | [9 empty] | 250 |  | 1 | [11 empty] | 2400 |  |  | P&D for 7" casing and core boxes | 10090 | 11710 | 16541
| NS |  | 4 | 560 | 12820 |  | 13.9 |  |  |  | 13.9 | 2571.5 | 5735 | 0.75 |  | 6.25 |  |  | 0.5 |  | 2550 | 12212.5 |  |  |  |  | 0 | 2850 | [27 empty] | 0 | 11710 | 5681.5
2021-01-25 | DS |  | 5 | 700 | 13520 | 18 |  |  |  |  | 18 | 0 | 5735 | 0.5 | 3 | 1.25 |  | 5.25 | 2 |  | 5531.25 | 17743.75 | 1 | 1 | 1 | 1 | 950 | 3800 | 18 |  |  | 1 | [19 empty] | 350 | 4200 |  | Cement and P&D for Piezo Installs | 5840 | 17550 | 13021.25
| NS |  | 4 | 560 | 14080 |  | 43.1 |  |  |  | 43.1 | 7973.5 | 13708.5 | 0.75 |  | 1.75 |  |  | 0.5 |  | 1087.5 | 18831.25 |  |  |  |  | 0 | 3800 | [27 empty] | 0 | 17550 | 9621
2021-01-26 | DS |  | 9 | 1260 | 15340 | [5 empty] | 0 | 0 | 13708.5 | 0.5 | 4.5 | 2.25 | 4.75 |  |  |  | 4493.75 | 23325 | 1 | 1 | 1 | 1 | 950 | 4750 | [17 empty] | 2 | 1 |  | 48 | 5 | 63 |  | 2800 |  | Piezo tremmie pipe 1"/500m | 2830 | 20380 | 9533.75
| NS |  | 4 | 560 | 15900 | 9 | 9.3 |  |  |  | 18.3 | 1720.5 | 15429 | 0.5 | 2.75 |  |  | 2.25 | 2 |  | 3393.75 | 26718.75 |  |  |  |  | 0 | 4750 | 9 |  |  | 1 | [7 empty] | 1 | [15 empty] | 985 | 21365 | 6659.25
2021-01-27 | DS |  | 5 | 700 | 16600 |  | 24.8 |  |  |  | 24.8 | 4588 | 20017 | 0.5 | [6 empty] | 162.5 | 26881.25 | 1 | 1 | 1 | 1 | 950 | 5700 | [11 empty] | 1 | [15 empty] | 190 | 21555 | 6590.5
| NS |  | 4 | 560 | 17160 |  | 24.2 |  |  |  | 24.2 | 4477 | 24494 | 0.5 |  |  |  |  | 1 |  | 712.5 | 27593.75 |  |  |  |  | 0 | 5700 | [27 empty] | 0 | 21555 | 5749.5
2021-01-28 | DS |  | 5 | 700 | 17860 |  | 10.8 |  |  |  | 10.8 | 1998 | 26492 | 0.5 |  |  |  |  | 2 |  | 1262.5 | 28856.25 | 1 | 1 | 1 | 1 | 950 | 6650 | [11 empty] | 1 | [15 empty] | 190 | 21745 | 5100.5
| NS |  | 4 | 560 | 18420 |  | 22 |  |  |  | 22 | 4070 | 30562 | 0.75 |  | 1 |  |  | 1.75 |  | 1531.25 | 30387.5 |  |  |  |  | 0 | 6650 | [27 empty] | 0 | 21745 | 6161.25
2021-01-29 | DS |  | 5 | 700 | 19120 | [5 empty] | 0 | 0 | 30562 | 0.5 | 3 | 4.75 |  |  | 0.75 |  | 3093.75 | 33481.25 | 1 | 1 | 1 | 1 | 950 | 7600 | [14 empty] | 1 |  |  |  | 2 | 1 | 27 |  | 24 |  | 300 |  | bladder air line (300') | 1193 | 22938 | 5936.75
| NS |  | 4 | 560 | 19680 | 12 | 20.8 |  |  |  | 32.8 | 3848 | 34410 | 0.5 | 1 |  |  | 3 | 1 |  | 2687.5 | 36168.75 |  |  |  |  | 0 | 7600 | 12 |  |  | 1 | [7 empty] | 1 | [15 empty] | 1150 | 24088 | 8245.5
2021-01-30 | DS |  | 5 | 700 | 20380 |  | 27 |  |  |  | 27 | 4995 | 39405 | 2 | [6 empty] | 650 | 36818.75 | 1 | 1 | 1 | 1 | 950 | 8550 | [20 empty] | 2 | 4 | [5 empty] | 0 | 24088 | 7295
| NS |  | 4 | 560 | 20940 |  | 36 |  |  |  | 36 | 6660 | 46065 | 0.5 | [6 empty] | 162.5 | 36981.25 |  |  |  |  | 0 | 8550 | [27 empty] | 0 | 24088 | 7382.5
2021-01-31 | DS |  | 5 | 700 | 21640 |  | 27 |  |  |  | 27 | 4995 | 51060 | 0.5 | [6 empty] | 162.5 | 37143.75 | 1 | 1 | 1 | 1 | 950 | 9500 | [11 empty] | 1 | [15 empty] | 190 | 24278 | 6997.5
| NS |  | 4 | 560 | 22200 |  | 33 |  |  |  | 33 | 6105 | 57165 | 0.5 | [6 empty] | 162.5 | 37306.25 |  |  |  |  | 0 | 9500 | [27 empty] | 0 | 24278 | 6827.5 | 22200 | 57165 | 37306.25 | 9500 | 24278 | 150449.25 | 7522.4625 | 157971.7125 | 157971.88
2021-02-01 | DS |  | 5 | 700 | 22900 |  | 27 |  |  |  | 27 | 4995 | 62160 | 0.5 | [6 empty] | 162.5 | 37468.75 | 1 | 1 | 1 | 1 | 950 | 10450 | [6 empty] | 1702.25 | [20 empty] | 1702.25 | 25980.25 | 8509.75
| NS |  | 4 | 560 | 23460 |  | 12.2 |  |  |  | 12.2 | 2257 | 64417 | 0.75 |  | 6.5 |  |  | 0.75 |  | 2768.75 | 40237.5 |  |  |  |  | 0 | 10450 | [27 empty] | 0 | 25980.25 | 5585.75
2021-02-02 | DS |  | 5 | 700 | 24160 | [5 empty] | 0 | 0 | 64417 | 0.5 |  |  | 11.5 |  |  |  | 5337.5 | 45575 | 1 | 1 | 1 | 1 | 950 | 11400 | [20 empty] | 70 | 10 | 63 |  |  | 80 |  | 0 | 25980.25 | 6987.5
| NS |  | 4 | 560 | 24720 | [5 empty] | 0 | 0 | 64417 | 4 | 8 | [5 empty] | 3900 | 49475 |  |  |  |  | 0 | 11400 | [27 empty] | 0 | 25980.25 | 4460
2021-02-03 | DS |  | 10 | 1400 | 26120 | 11.35 |  |  |  |  | 11.35 | 0 | 64417 | 1.5 | 6 |  |  | 3.5 | 1 |  | 4912.5 | 54387.5 | 1 | 1 | 1 | 1 | 950 | 12350 | 12 |  |  | 1 | [23 empty] | 960 | 26940.25 | 8222.5
| NS |  | 4 | 560 | 26680 |  | 12.5 |  |  |  | 12.5 | 2312.5 | 66729.5 | 3.5 |  |  |  | 0.5 |  |  | 1412.5 | 55800 |  |  |  |  | 0 | 12350 | [27 empty] | 0 | 26940.25 | 4285
2021-02-04 | DS |  | 5 | 700 | 27380 |  | 18 |  |  |  | 18 | 3330 | 70059.5 | 0.75 |  |  |  |  | 1 |  | 793.75 | 56593.75 | 1 | 1 | 1 | 1 | 950 | 13300 | [11 empty] | 1 | [15 empty] | 190 | 27130.25 | 5963.75
| NS |  | 4 | 560 | 27940 |  | 15.3 |  |  |  | 15.3 | 2830.5 | 72890 | 0.5 | [6 empty] | 162.5 | 56756.25 |  |  |  |  | 0 | 13300 | [27 empty] | 0 | 27130.25 | 3553
2021-02-05 | DS |  | 5 | 700 | 28640 |  | 7.5 |  |  |  | 7.5 | 1387.5 | 74277.5 | 3 |  |  |  |  | 1.5 |  | 1800 | 58556.25 | 1 | 1 | 1 | 1 | 950 | 14250 | [27 empty] | 0 | 27130.25 | 4837.5
| NS |  | 4 | 560 | 29200 |  | 10.4 |  |  |  | 10.4 | 1924 | 76201.5 | 0.75 |  | 1.75 |  | 0.5 | 2.25 |  | 2325 | 60881.25 |  |  |  |  | 0 | 14250 | [6 empty] | 1548 | [20 empty] | 1548 | 28678.25 | 6357
2021-02-06 | DS |  | 5 | 700 | 29900 | 12 | 8.55 |  |  |  | 20.55 | 1581.75 | 77783.25 | 0.5 | 1.75 | 3.5 |  | 2.75 | 0.5 |  | 3656.25 | 64537.5 | 1 | 1 | 1 | 1 | 950 | 15200 | 12 |  |  | 1 | [23 empty] | 960 | 29638.25 | 7848
| NS |  | 4 | 560 | 30460 |  | 21 |  |  |  | 21 | 3885 | 81668.25 | 1.75 | [6 empty] | 568.75 | 65106.25 |  |  |  |  | 0 | 15200 | [27 empty] | 0 | 29638.25 | 5013.75
2021-02-07 | DS |  | 5 | 700 | 31160 |  | 19 |  |  |  | 19 | 3515 | 85183.25 | 2 | [6 empty] | 650 | 65756.25 | 1 | 1 | 1 | 1 | 950 | 16150 | [11 empty] | 1 | [15 empty] | 190 | 29828.25 | 6005
| NS |  | 4 | 560 | 31720 |  | 15 |  |  |  | 15 | 2775 | 87958.25 | 2.5 | [6 empty] | 812.5 | 66568.75 |  |  |  |  | 0 | 16150 | [27 empty] | 0 | 29828.25 | 4147.5
2021-02-08 | DS |  | 5 | 700 | 32420 |  | 8.25 |  |  |  | 8.25 | 1526.25 | 89484.5 | 6.5 |  |  |  |  | 2.5 |  | 3487.5 | 70056.25 | 1 | 1 | 1 | 1 | 950 | 17100 | [6 empty] | 3200 | [20 empty] | 3200 | 33028.25 | 9863.75
| NS |  | 4 | 560 | 32980 | [5 empty] | 0 | 0 | 89484.5 | 2 | 4.75 | 4.25 |  |  | 1 |  | 4125 | 74181.25 |  |  |  |  | 0 | 17100 | [27 empty] | 0 | 33028.25 | 4685
2021-02-09 | DS |  | 10 | 1400 | 34380 | [5 empty] | 0 | 0 | 89484.5 | 0.5 | 1 |  | 10.5 |  |  |  | 5212.5 | 79393.75 | 1 | 1 | 1 | 1 | 950 | 18050 | [18 empty] | 1 |  | 52 | 6 | 81 |  |  |  |  | 5 | 33033.25 | 7567.5
| NS |  | 4 | 560 | 34940 | 15 |  |  |  |  | 15 | 0 | 89484.5 | 0.5 | 5.5 |  |  | 6 |  |  | 5250 | 84643.75 |  |  |  |  | 0 | 18050 | 15 |  |  | 1 | [23 empty] | 1125 | 34158.25 | 6935
2021-02-10 | DS |  | 5 | 700 | 35640 | 6 |  |  |  |  | 6 | 0 | 89484.5 | 1.5 |  |  |  | 3.25 | 5.75 |  | 5437.5 | 90081.25 | 1 | 1 | 1 | 1 | 950 | 19000 | 6 | [10 empty] | 1 | [15 empty] | 520 | 34678.25 | 7607.5
| NS |  | 4 | 560 | 36200 | 3 |  |  |  |  | 3 | 0 | 89484.5 | 9 |  |  |  | 1.5 |  |  | 3750 | 93831.25 |  |  |  |  | 0 | 19000 | 3 | [26 empty] | 165 | 34843.25 | 4475
2021-02-11 | DS |  | 5 | 700 | 36900 | 9 |  |  |  |  | 9 | 0 | 89484.5 | 0.5 |  |  |  | 4.75 |  |  | 2775 | 96606.25 | 1 | 1 | 1 | 1 | 950 | 19950 | 9 | [23 empty] | 3454.56 |  | 145 cement bags brought in (199 used on their list from the initial 145 bags brought in so good) | 3949.56 | 38792.81 | 8374.56
| NS |  | 4 | 560 | 37460 | 3 | 18.1 |  |  |  | 21.1 | 3348.5 | 92833 | 1.5 |  |  |  | 1 | 1 |  | 1587.5 | 98193.75 |  |  |  |  | 0 | 19950 | 3 | [26 empty] | 165 | 38957.81 | 5661
2021-02-12 | DS |  | 5 | 700 | 38160 |  | 45.8 |  |  |  | 45.8 | 8473 | 101306 | 0.5 | [6 empty] | 162.5 | 98356.25 | 1 | 1 | 1 | 1 | 950 | 20900 | [27 empty] | 0 | 38957.81 | 10285.5
| NS |  | 4 | 560 | 38720 |  | 4.1 |  |  |  | 4.1 | 758.5 | 102064.5 | 0.75 | 2.5 | 5 |  |  | 0.75 |  | 3093.75 | 101450 |  |  |  |  | 0 | 20900 | [27 empty] | 0 | 38957.81 | 4412.25
2021-02-13 | DS |  | 5 | 700 | 39420 | 24 |  |  |  |  | 24 | 0 | 102064.5 | 0.5 |  |  |  | 6 |  |  | 3462.5 | 104912.5 | 1 | 1 | 1 | 1 | 950 | 21850 | 24 |  |  | 1 | [8 empty] | 1 | [14 empty] | 1770 | 40727.81 | 6882.5
| NS |  | 4 | 560 | 39980 | 12 |  |  |  |  | 12 | 0 | 102064.5 | 0.5 |  |  |  | 5 |  |  | 2912.5 | 107825 |  |  |  |  | 0 | 21850 | 12 | [26 empty] | 660 | 41387.81 | 4132.5
2021-02-14 | DS |  | 5 | 700 | 40680 | 6 | 26.85 |  |  |  | 32.85 | 4967.25 | 107031.75 | 1 |  |  |  | 1 | 1 |  | 1425 | 109250 | 1 | 1 | 1 | 1 | 950 | 22800 | 6 | [5 empty] | 1240 | [20 empty] | 1570 | 42957.81 | 9612.25
| NS |  | 4 | 560 | 41240 |  | 48.15 |  |  |  | 48.15 | 8907.75 | 115939.5 | 0.5 | [6 empty] | 162.5 | 109412.5 |  |  |  |  | 0 | 22800 | [11 empty] | 1 | [15 empty] | 190 | 43147.81 | 9820.25
2021-02-15 | DS |  | 5 | 700 | 41940 | [5 empty] | 0 | 0 | 115939.5 | 0.5 |  | 5 | 6 |  | 0.5 |  | 4762.5 | 114175 | 1 | 1 | 1 | 1 | 950 | 23750 | [6 empty] | 1398 | [11 empty] | 1 |  | 52 | 7 | 117 |  |  | 50 |  | 1403 | 44550.81 | 7815.5
| NS |  | 4 | 560 | 42500 | [5 empty] | 0 | 0 | 115939.5 | 12 | [6 empty] | 3900 | 118075 |  |  |  |  | 0 | 23750 | [24 empty] | 6090 |  |  | 6090 | 50640.81 | 10550 | 20300 | 58774.5 | 80768.75 | 14250 | 26362.81 | 200456.06 | 10022.803 | 210478.863 | 210479.18
2021-02-16 | DS |  | 5 | 700 | 43200 | 9 |  |  |  | 33.55 | 42.55 | 2348.5 | 118288 | 1 | 4 |  |  | 2 | 1 |  | 3275 | 121350 | 1 | 1 | 1 | 1 | 950 | 24700 | 9 |  |  | 1 |  |  | 3270 | [20 empty] | 4065 | 54705.81 | 11338.5
| NS |  | 4 | 560 | 43760 |  |  |  |  | 79.45 | 79.45 | 5561.5 | 123849.5 | 0.75 |  | 3.5 |  |  | 1.25 |  | 2068.75 | 123418.75 |  |  |  |  | 0 | 24700 | [7 empty] | 1 | [15 empty] | 2400 |  |  | Hot shot delivery 311mm casing & 9" pipe | 2940 | 57645.81 | 11130.25
2021-02-17 | DS |  | 5 | 700 | 44460 | 9 |  |  |  |  | 9 | 0 | 123849.5 | 1.5 | 5.75 |  |  |  |  | 3.75 | 5037.5 | 128456.25 | 1 | 1 | 1 | 1 | 950 | 25650 |  |  | 9 |  |  | 1 | [18 empty] | 360 | 6 | 4 piezo's @ $90 | 1652 | 59297.81 | 8339.5
| NS |  | 4 | 560 | 45020 | 9.7 |  |  |  |  | 9.7 | 0 | 123849.5 | 1 | [5 empty] | 3 | 2470 | 130926.25 |  |  |  |  | 0 | 25650 | [11 empty] | 1 | [15 empty] | 190 | 59487.81 | 3220
2021-02-18 | DS |  | 5 | 700 | 45720 | 18.3 |  |  |  |  | 18.3 | 0 | 123849.5 | 0.5 | [5 empty] | 11.5 | 8385 | 139311.25 | 1 | 1 | 1 | 1 | 950 | 26600 | [13 empty] | 1 | [13 empty] | 160 | 59647.81 | 10195
| NS |  | 4 | 560 | 46280 | 14 |  |  |  |  | 14 | 0 | 123849.5 | 0.5 | [5 empty] | 11.5 | 8385 | 147696.25 |  |  |  |  | 0 | 26600 | [27 empty] | 0 | 59647.81 | 8945
2021-02-19 | DS |  | 5 | 700 | 46980 | 6.72 |  |  |  |  | 6.72 | 0 | 123849.5 | 0.5 | [5 empty] | 11.5 | 8385 | 156081.25 | 1 | 1 | 1 | 1 | 950 | 27550 | [11 empty] | 1 | [15 empty] | 190 | 59837.81 | 10225
| NS |  | 4 | 560 | 47540 | 12.2 |  |  |  |  | 12.2 | 0 | 123849.5 | 0.5 | [5 empty] | 11.5 | 8385 | 164466.25 |  |  |  |  | 0 | 27550 | [27 empty] | 0 | 59837.81 | 8945
2021-02-20 | DS |  | 5 | 700 | 48240 | 18.3 |  |  |  |  | 18.3 | 0 | 123849.5 | 0.5 | [5 empty] | 11.5 | 8385 | 172851.25 | 1 | 1 | 1 | 1 | 950 | 28500 | [11 empty] | 1 | [15 empty] | 190 | 60027.81 | 10225
| NS |  | 4 | 560 | 48800 | 3.2 |  |  |  |  | 3.2 | 0 | 123849.5 | 8.5 | [5 empty] | 3.5 | 5265 | 178116.25 |  |  |  |  | 0 | 28500 | [27 empty] | 0 | 60027.81 | 5825
2021-02-21 | DS |  | 5 | 700 | 49500 | [5 empty] | 0 | 0 | 123849.5 | 8 | [6 empty] | 2600 | 180716.25 |  |  |  |  | 0 | 28500 | [27 empty] | 0 | 60027.81 | 3300
| NS |  | 4 | 560 | 50060 | [5 empty] | 0 | 0 | 123849.5 | 8 | [6 empty] | 2600 | 183316.25 |  |  |  |  | 0 | 28500 | [27 empty] | 0 | 60027.81 | 3160
2021-02-22 | DS |  | 5 | 700 | 50760 | [5 empty] | 0 | 0 | 123849.5 | 8 | [6 empty] | 2600 | 185916.25 |  |  |  |  | 0 | 28500 | [27 empty] | 0 | 60027.81 | 3300
| NS |  | 4 | 560 | 51320 | 21.2 |  |  |  |  | 21.2 | 0 | 123849.5 | 3 | [5 empty] | 9 | 7410 | 193326.25 |  |  |  |  | 0 | 28500 | [11 empty] | 1 | [15 empty] | 190 | 60217.81 | 8160
2021-02-23 | DS |  | 5 | 700 | 52020 | 5 |  |  |  |  | 5 | 0 | 123849.5 | 0.5 | 5 |  |  |  |  | 6.5 | 6435 | 199761.25 | 1 | 1 | 1 | 1 | 950 | 29450 | [27 empty] | 0 | 60217.81 | 8085
| NS |  | 4 | 560 | 52580 | 9 |  |  |  |  | 9 | 0 | 123849.5 | 3 | 2 |  |  |  |  | 6 | 5915 | 205676.25 |  |  |  |  | 0 | 29450 |  |  | 9 |  |  | 1 | [19 empty] | 8 |  | 1292 | 61509.81 | 7767
2021-02-24 | DS |  | 10 | 1400 | 53980 | 22.3 |  |  |  |  | 22.3 | 0 | 123849.5 | 3.5 | [5 empty] | 8.5 | 7215 | 212891.25 | 1 | 1 | 1 | 1 | 950 | 30400 | [8 empty] | 1 | [18 empty] | 4200 | 65709.81 | 13765
| NS |  | 4 | 560 | 54540 | 23.7 |  |  |  |  | 23.7 | 0 | 123849.5 | 0.5 | [5 empty] | 11.5 | 8385 | 221276.25 |  |  |  |  | 0 | 30400 | [27 empty] | 0 | 65709.81 | 8945
2021-02-25 | DS |  | 5 | 700 | 55240 | 14.62 |  |  |  |  | 14.62 | 0 | 123849.5 | 1 | [5 empty] | 11 | 8190 | 229466.25 | 1 | 1 | 1 | 1 | 950 | 31350 | [27 empty] | 0 | 65709.81 | 9840
| NS |  | 4 | 560 | 55800 | 20.88 |  |  |  |  | 20.88 | 0 | 123849.5 | 0.5 | [5 empty] | 11.5 | 8385 | 237851.25 |  |  |  |  | 0 | 31350 | [27 empty] | 0 | 65709.81 | 8945
2021-02-26 | DS |  | 5 | 700 | 56500 | 19.37 |  |  |  |  | 19.37 | 0 | 123849.5 | 0.5 | [5 empty] | 11.5 | 8385 | 246236.25 | 1 | 1 | 1 | 1 | 950 | 32300 | [11 empty] | 1 | [15 empty] | 190 | 65899.81 | 10225
| NS |  | 4 | 560 | 57060 | 8.1 |  |  |  |  | 8.1 | 0 | 123849.5 | 0.5 | 3.5 |  |  |  |  | 8 | 7020 | 253256.25 |  |  |  |  | 0 | 32300 | [27 empty] | 0 | 65899.81 | 7580
2021-02-27 | DS |  | 5 | 700 | 57760 | 9 |  |  |  |  | 9 | 0 | 123849.5 | 6 | [5 empty] | 6 | 6240 | 259496.25 | 1 | 1 | 1 | 1 | 950 | 33250 |  |  | 9 |  |  | 1 | [19 empty] | 11 |  | 1292 | 67191.81 | 9182
| NS |  | 4 | 560 | 58320 | 17 |  |  |  |  | 17 | 0 | 123849.5 | 3 | [5 empty] | 5.5 | 4907.5 | 264403.75 |  |  |  |  | 0 | 33250 | [27 empty] | 0 | 67191.81 | 5467.5
2021-02-28 | DS |  | 5 | 700 | 59020 | 29 |  |  |  |  | 29 | 0 | 123849.5 | 0.5 | [5 empty] | 11.5 | 8385 | 272788.75 | 1 | 1 | 1 | 1 | 950 | 34200 | [27 empty] | 0 | 67191.81 | 10035
| NS |  | 4 | 560 | 59580 | 15.32 |  |  |  |  | 15.32 | 0 | 123849.5 | 1 | [5 empty] | 11 | 8190 | 280978.75 |  |  |  |  | 0 | 34200 | [13 empty] | 1 | [13 empty] | 160 | 67351.81 | 8910 | 17080 | 7910 | 162903.75 | 10450 | 16711 | 215054.75 | 10752.7375 | 225807.4875
2021-03-01 | DS |  | 5 | 700 | 60280 | 18.3 |  |  |  |  | 18.3 | 0 | 123849.5 | 1.5 | [5 empty] | 10.5 | 7995 | 288973.75 | 1 | 1 | 1 | 1 | 950 | 35150 | [27 empty] | 0 | 67351.81 | 9645
| NS |  | 4 | 560 | 60840 | 21 |  |  |  |  | 21 | 0 | 123849.5 | 0.5 | [5 empty] | 11.5 | 8385 | 297358.75 |  |  |  |  | 0 | 35150 | [11 empty] | 1 | [15 empty] | 190 | 67541.81 | 9135
2021-03-02 | DS |  | 10 | 1400 | 62240 | 9.4 |  |  |  |  | 9.4 | 0 | 123849.5 | 1 | 3 |  |  |  |  | 8 | 7020 | 304378.75 | 1 | 1 | 1 | 1 | 950 | 36100 | [27 empty] | 0 | 67541.81 | 9370
| NS |  | 4 | 560 | 62800 | 9 |  |  |  |  | 9 | 0 | 123849.5 | 4.5 | 2.5 |  |  |  |  | 5 | 5850 | 310228.75 |  |  |  |  | 0 | 36100 |  |  | 9 |  |  | 1 | [20 empty] | Set of wings for 12 3/4" Odex driver | 1292 | 68833.81 | 7702
2021-03-03 | DS |  | 5 | 700 | 63500 | 34 |  |  |  |  | 34 | 0 | 123849.5 | 2.5 | [5 empty] | 9.5 | 7605 | 317833.75 | 1 | 1 | 1 | 1 | 950 | 37050 | [27 empty] | 0 | 68833.81 | 9255
| NS |  | 4 | 560 | 64060 | 18.12 |  |  |  |  | 18.12 | 0 | 123849.5 | 0.5 | [5 empty] | 11.5 | 8385 | 326218.75 |  |  |  |  | 0 | 37050 | [8 empty] | 1 | [18 empty] | 4200 | 73033.81 | 13145
2021-03-04 | DS |  | 5 | 700 | 64760 | 18.6 |  |  |  |  | 18.6 | 0 | 123849.5 | 0.5 | [5 empty] | 7.5 | 5525 | 331743.75 | 1 | 1 | 1 | 1 | 950 | 38000 | [11 empty] | 1 |  | 1 | [13 empty] | 350 | 73383.81 | 7525
| NS |  | 4 | 560 | 65320 | 26.5 |  |  |  |  | 26.5 | 0 | 123849.5 | 0.5 | [5 empty] | 11.5 | 8385 | 340128.75 |  |  |  |  | 0 | 38000 | [6 empty] | 1 | [20 empty] | 1 | 73384.81 | 8946
2021-03-05 | DS |  | 5 | 700 | 66020 | 8.62 |  |  |  |  | 8.62 | 0 | 123849.5 | 0.5 | 0.5 |  |  |  |  | 8.75 | 6581.25 | 346710 | 1 | 1 | 1 | 1 | 950 | 38950 | [6 empty] | 1 | [19 empty] | 4 12" casing caps | 1 | 73385.81 | 8232.25
| NS |  | 4 | 560 | 66580 | [5 empty] | 0 | 0 | 123849.5 | 0.5 | 11.5 | [5 empty] | 3900 | 350610 |  |  |  |  | 0 | 38950 | [27 empty] | 0 | 73385.81 | 4460
2021-03-06 | DS |  | 5 | 700 | 67280 | [5 empty] | 0 | 0 | 123849.5 | 6.5 | 4.5 | [5 empty] | 3575 | 354185 | 1 | 1 | 1 |  | 750 | 39700 | [27 empty] | 0 | 73385.81 | 5025
| NS |  |  | 0 | 67280 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-07 | DS | 1 |  | 7500 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 7500
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-08 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-09 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-10 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-11 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-12 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-13 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-14 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-15 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-16 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-17 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-18 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-19 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-20 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-21 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-22 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-23 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-24 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-25 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-26 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-27 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-28 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-29 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-30 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
2021-03-31 | DS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
| NS |  |  | 0 | 74780 | [5 empty] | 0 | 0 | 123849.5 | [7 empty] | 0 | 354185 |  |  |  |  | 0 | 39700 | [27 empty] | 0 | 73385.81 | 0
|  |  |  | 74780 | [6 empty] | 1382.5 | 123849.5 | [8 empty] | 354185 | [5 empty] | 39700 | [23 empty] | 152 |  |  |  |  | 73385.81 |  | 665900.31
Note on P10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: includes switch rig to coring and spot pipe truck
Note on BC12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 145 cement bags ($3000), 80 benny bags ($1200)
Note on E14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: crew change
Note on AV14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: i had 3
Note on AK17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 retip to be invoiced later. INVOICED Feb 1
Note on P19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: should be .75 with the .25 safety logger meeting
Note on AT20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: i had the 37m here
Note on E30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: crew switch out including Davin/Albert
Note on P31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: medic stuck so the on standby to help, wait on crew to arrive, mix mud for coring
Note on T31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: mixing mud at operating rate
Note on T33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: mixing mud at operating rate
Note on P34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: They drop core barrel and we pay standby for them to rig out the gear.
Note on T35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: circ and cond hole at hourly rate
Note on AK35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 bit retip to be charged later
Note on P37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: wait on water, everything freezing up
Note on P40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Poor drilling by crew. Should have tripped ages ago.
Note on AK40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 bit retip to be charged later
Note on P44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Safety, and switch to core/odex
Note on P45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8.5hr on standby due to "POLAR VORTEX :)"
Note on AK52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 bit retip to be charged later
Note on AK54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 bit retip to be charged later
Note on P55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 0.5 safety, 11.5hr move a few smalls to LD but have to wait for morning move to LD pad
Note on AK56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 odex driver retip
Note on P58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1hr cement casing shoe
Note on P65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Blizzard
Note on P66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8hrs standby due to weather
Note on P67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8hrs standby due to weather
Note on P68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8hrs standby due to weather
Note on Q70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Prep site for next hole including bumping rig, moving cyclone and hoses for bigger double sump, and major snow removal.
Note on P71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: includes wait on cement and switch rig to conventional
Note on P85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: wait on cement
Note on P86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes Ministry visit
Note on AJ104: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cut drill string due to soft pad. Hoe extracated new hammer
Note on AJ105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ring Bit for Symmetrix system
Note on AJ111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 30m suction line
Note on AJ132: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12" drive shoe
Note on AJ134: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $100 well head fitting, 3hr hot shot service to bring grout plant back ($165/hr)

## Avalanche
AVALANCHE | Shift | Truck Delivery (hr) | Chains/axle | Daily | Cumulative
4172.5 |  | 155 | 75 | Cost | Cost
2021-03-03 | DS | 5 | 1 | 850 | 850
| NS | 4 | 1 | 695 | 1545
2021-03-04 | DS | 5 | 1 | 850 | 2395
| NS | 6 | 1 | 1005 | 3400
2021-03-05 | DS | 4.5 | 1 | 772.5 | 4172.5
| NS |  |  | 0 | 4172.5
2021-03-06 | DS |  |  | 0 | 4172.5
| NS |  |  | 0 | 4172.5
2021-03-07 | DS |  |  | 0 | 4172.5
| NS |  |  | 0 | 4172.5
4172.5

## APEX
APEX | JH Daily Office Rate (2020) (hr) | JH Daily Office Rate (2021) (hr) | JH Daily Field Rate (2020) (hr) | JH Daily Field Rate (2021) (hr) | Adriana Matesoi Field Rate (hr) | Vesko Karadzic Field Rate (hr) | Karys Leonard-Fortune Field Rate (hr) | Karys Leonard-Fortune Office Rate (hr) | Other Apex Staff | Truck Rental (day) | Laptop Rental (day) | GPS Rental (day) | Core Camera | Expense Total | Accomodations | Overhead / management (10%) | Daily | Cumulative | Comments | Sub-Total | GST | Total | APEX INVOICE
94722.93 | 450 | 500 | 675 | 700 | 675 | 675 | 525 | 400 | 650 | 100 | 20 | 10 | 5 |  | 126.36 |  | Cost | Cost
2021-01-12 | 0.33 | 1 | [14 empty] | 648.5 | 648.5
2021-01-13 |  | 1 | [14 empty] | 500 | 1148.5
2021-01-14 |  | 0.54 | [5 empty] | 0.9 | [5 empty] | 766.22 |  |  | 1396.22 | 2544.72 | JH expenses
2021-01-15 | [16 empty] | 0 | 2544.72
2021-01-16 | [16 empty] | 0 | 2544.72
2021-01-17 | [16 empty] | 0 | 2544.72
2021-01-18 |  |  | 1 | [6 empty] | 1 | 1 | 1 |  |  |  |  | 805 | 3349.72
2021-01-19 |  |  | 1 | [6 empty] | 1 | 1 | 1 |  |  | 1 |  | 931.36 | 4281.08
2021-01-20 |  |  | 1 | [6 empty] | 1 | 1 | 1 |  |  | 1 |  | 931.36 | 5212.44
2021-01-21 |  |  | 1 | [6 empty] | 1 | 1 | 1 |  |  | 1 | 253.53 | 1184.89 | 6397.33 |  | 7787.29 | 389.3645 | 8176.6545 | 8176.65
2021-01-22 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 7353.69
2021-01-23 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 8310.05
2021-01-24 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 9266.41
2021-01-25 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 10222.77
2021-01-26 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 11179.13
2021-01-27 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 12135.49
2021-01-28 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 13091.85
2021-01-29 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 14048.21
2021-01-30 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 15004.57
2021-01-31 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 15960.93
2021-02-01 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 16917.29
2021-02-02 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 17873.65
2021-02-03 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 18830.01
2021-02-04 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 19786.37
2021-02-05 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 20742.73
2021-02-06 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 21699.09
2021-02-07 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 22655.45
2021-02-08 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 23611.81
2021-02-09 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 24568.17
2021-02-10 |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 | 1 |  |  | 1 |  | 1631.36 | 26199.53
2021-02-11 |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 | 1 |  | 3019.31 | 1 |  | 4650.67 | 30850.2 | JH expenses
2021-02-12 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  | 1 |  | 956.36 | 31806.56
2021-02-13 |  |  |  | 1 |  |  | 1 |  |  | 2 | 2 | 1 | 1 | 476.83 | 2 |  | 2204.55 | 34011.11 | Karys Flight
2021-02-14 |  |  |  | 1 |  |  | 1 |  |  | 2 | 2 | 1 | 1 |  | 2 |  | 1727.72 | 35738.83
2021-02-15 |  |  |  | 1 | [5 empty] | 2 | 2 | 1 | 1 |  | 1 |  | 1076.36 | 36815.19
2021-02-16 |  |  |  | 1 | 1 | 1 |  |  |  | 2 | 2 | 1 | 1 |  | 1 |  | 2426.36 | 39241.55
2021-02-17 |  |  |  | 1 | 1 | 0.3 |  |  |  | 2 | 2 | 1 | 1 |  | 1 |  | 1953.86 | 41195.41
2021-02-18 |  |  |  | 1 | 1 |  | 1 |  |  | 3 | 2 | 1 | 1 | 587.81 | 2 |  | 3090.53 | 44285.94 | Karys Flight
2021-02-19 |  |  |  | 1 | 1 |  | 1 |  |  | 3 | 2 | 1 | 1 |  | 2 |  | 2502.72 | 46788.66
2021-02-20 |  |  |  | 1 | 1 |  | 1 |  |  | 3 | 2 | 1 | 1 |  | 2 |  | 2502.72 | 49291.38
2021-02-21 |  |  |  | 1 | 1 |  | 1 |  |  | 3 | 2 | 1 | 1 |  | 2 |  | 2502.72 | 51794.1
2021-02-22 |  |  |  | 1 | 1 |  | 1 |  |  | 3 | 2 | 1 | 1 |  | 2 |  | 2502.72 | 54296.82
2021-02-23 |  |  |  | 1 | 1 |  | 1 |  |  | 3 | 2 | 1 | 1 |  | 2 |  | 2502.72 | 56799.54
2021-02-24 |  |  |  | 1 | 1 |  | 1 |  |  | 3 | 2 | 1 | 1 |  | 2 |  | 2502.72 | 59302.26
2021-02-25 |  |  |  | 1 | 1 |  | 1 |  |  | 3 | 2 | 1 | 1 | 327.21 | 2 |  | 2829.93 | 62132.19 | Deakin order
2021-02-26 |  |  |  | 1 | 1 |  | 1 |  |  | 3 | 2 | 1 | 1 | 1113.21 | 2 |  | 3615.93 | 65748.12 | IRL order
2021-02-27 |  |  |  | 1 | 1 |  | 1 |  |  | 3 | 2 | 1 | 1 |  | 2 |  | 2502.72 | 68250.84
2021-02-28 |  |  |  | 1 | 1 |  | 1 |  |  | 3 | 2 | 1 | 1 | 1911.18 | 2 |  | 4413.9 | 72664.74 | JH expenses
2021-03-01 |  |  |  | 1 | 1 |  | 1 |  |  | 3 | 2 | 1 | 1 | 1994.93 | 2 |  | 4497.65 | 77162.39 | Karys expenses
2021-03-02 |  |  |  | 1 | 1 |  | 1 |  |  | 3 | 2 | 1 | 1 | 532.86 | 2 |  | 3035.58 | 80197.97 | Adriana expenses
2021-03-03 |  |  |  | 1 | 1 |  | 1 |  |  | 3 | 2 | 1 | 1 |  | 2 |  | 2502.72 | 82700.69
2021-03-04 |  |  |  | 1 | 1 |  | 1 |  |  | 3 | 2 | 1 | 1 |  | 2 |  | 2502.72 | 85203.41
2021-03-05 |  |  |  | 1 | 1 |  | 1 |  |  | 3 | 2 | 1 | 1 |  | 2 |  | 2502.72 | 87706.13
2021-03-06 |  |  |  | 1 |  |  | 1 |  |  | 3 | 2 | 1 | 1 |  | 2 |  | 1827.72 | 89533.85
2021-03-07 |  |  |  | 1 |  |  | 1 |  |  | 3 | 2 | 1 | 1 |  | 2 |  | 1827.72 | 91361.57
2021-03-08 |  |  |  | 1 |  |  | 1 |  |  | 3 | 2 | 1 | 1 |  | 1 |  | 1701.36 | 93062.93
2021-03-09 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  |  |  | 830 | 93892.93
2021-03-10 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  |  |  |  | 830 | 94722.93
2021-03-11 | [16 empty] | 0 | 94722.93
2021-03-12 | [16 empty] | 0 | 94722.93
2021-03-13 | [16 empty] | 0 | 94722.93
2021-03-14 | [16 empty] | 0 | 94722.93
2021-03-15 | [16 empty] | 0 | 94722.93
2021-03-16 | [16 empty] | 0 | 94722.93
2021-03-17 | [16 empty] | 0 | 94722.93
2021-03-18 | [16 empty] | 0 | 94722.93
2021-03-19 | [16 empty] | 0 | 94722.93
2021-03-20 | [16 empty] | 0 | 94722.93
2021-03-21 | [16 empty] | 0 | 94722.93
2021-03-22 | [16 empty] | 0 | 94722.93
2021-03-23 | [16 empty] | 0 | 94722.93
2021-03-24 | [16 empty] | 0 | 94722.93
2021-03-25 | [16 empty] | 0 | 94722.93
2021-03-26 | [16 empty] | 0 | 94722.93
2021-03-27 | [16 empty] | 0 | 94722.93
2021-03-28 | [16 empty] | 0 | 94722.93
2021-03-29 | [16 empty] | 0 | 94722.93
2021-03-30 | [16 empty] | 0 | 94722.93
2021-03-31 | [16 empty] | 0 | 94722.93
94722.93
Note on P10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Jan 19-Feb1 on Jan 21 Invoice

## Summary
DR-1 & DR-3
Company | Requisition Total | Total to date | Cost / metre | Balance | Comments
4Evergreen | 224520 | 154552.5 |  | 69967.5 | No Invoice
Good Earth | 655851 | 665900.31 | 481.6639 | -10049.31 | Invoices
Century | 76195 | 73392.26 |  | 2802.74 | No Invoice
Piteau | 75121.88 | 88429.291 |  | -13307.411 | Invoices
APEX | 97385 | 94722.93 |  | 2662.07 | Invoices
Avalanche | 8680 | 4172.5 |  | 4507.5 | Invoices
| 1137752.88 | 1081169.791 | 782.0396 | 52075.589
DR-2 Program
Company | Requisition Total | Total to date | Cost / metre | Balance | Comments
Geotech | 31655.62 | 38925.439 | 437.2662 | -7269.819 | Invoiced
Ecofor | 16200 | 13637.5 |  | 2562.5 | No Invoice
Wood | 76624 | 12023 |  | 64601 | No Invoice
LORAX??? |  |  |  | 0 | No Invoice
| 124479.62 | 64585.939 | 725.5217 | 59893.681