## HR21HQ-01
Conuma Coal Hermann Mine Amendment Program - January 2021 |  |  |  |  | Good Earth Drilling
Proposed HOLE ID: | HC-1a
HOLE ID | HR20HQ-01 |  |  |  | Drill Progress
Target Depth: | 55 | Metres |  |  | 5 | no. of Shifts
Casing: | 24 | Metres |  |  | 55 | m to date
Azm : | 215 | Deg |  |  | 11 | m/shift (avg.)
Inclination: | -60 | Deg |  |  | -1.8182e-07 | shifts to target
Northing: | 6097496 | mN |  |  | DDH Start | 22/01/2021
Easting: | 618718 | mE |  |  | DDH Finish | 25/01/2022
Date | Shift | SHIFT | CUMULATIVE | COMMENTS
|  | Metres | Metres
2021-01-22 | D | 0 | 0.0 | Mob in equipment and setup on proposed hole HC-1A
| N | 0 | 0.0 | No NS
2021-01-23 | D | 1e-06 | 1e-06 | Rig mechanical, likely hydraulic pump.
| N | 24 | 24 | Rig repair completed by 2345 hrs (main hydraulic pump), set casing at 24m.
2021-01-24 | D | 17 | 41 | Rig up for coring, core hole from 24m to 41m.
| N | 14 | 55 | Coring from 41m to 55m TD, rig up for logging, logging hole.
2021-01-25 | D | 1e-06 | 55 | Complete logging, tear down, prep to bump rig

## HR21HQ-02
Conuma Coal Hermann Mine Amendment Program - January 2021 |  |  |  |  | Good Earth Drilling
Proposed HOLE ID: | HC-2v
HOLE ID | HR20HQ-02 |  |  |  | Drill Progress
Target Depth: | 61 | Metres |  |  | 3 | no. of Shifts
Casing: | 18 | Metres |  |  | 61.1 | m to date
Azm : | n.a. | Deg |  |  | 20.3667 | m/shift (avg.)
Inclination: | -90 | Deg |  |  | -0.00491 | shifts to target
Northing: | 6097488 | mN |  |  | DDH Start | 2021-01-25
Easting: | 618700 | mE |  |  | DDH Finish | 2021-01-26
Date | Shift | SHIFT | CUMULATIVE | COMMENTS
|  | Metres | Metres
2021-01-25 | D | 18 | 18 | Bump rig from HR20HQ-01, rig up, spud hole, set casing to 18m, rig up for coring
| N | 43.1 | 61.1 | Coring from 18m to 61m, rig up for logging, log hole
2021-01-26 | D | 1e-06 | 61.1 | Complete logging, install vwp, tear down, move rig to proposed hole MB-1a

## HR21HQ-03
Conuma Coal Hermann Mine Amendment Program - January 2021 |  |  |  |  | Good Earth Drilling
Proposed HOLE ID: | MB-1a
HOLE ID | HR20HQ-03 |  |  |  | Drill Progress
Target Depth: | 100 | Metres |  |  | 7 | no. of Shifts
Casing: | 9.1 | Metres |  |  | 100.1 | m to date
Azm : | 225 | Deg |  |  | 14.3 | m/shift (avg.)
Inclination: | -60 | Deg |  |  | -0.0069944 | shifts to target
Northing: | 6096800 | mN |  |  | DDH Start | 2021-01-26
Easting: | 618297 | mE |  |  | DDH Finish | 2021-01-29
Date | Shift | SHIFT | CUMULATIVE | COMMENTS
|  | Metres | Metres
2021-01-26 | D | 1e-05 | 1e-05 | Moving rig from HR20HQ-02, rigging up
| N | 18.3 | 18.3 | Complete rig move, rig up, set casing to 9.1m, rig up to core, coring from 9.10 m to 18.30 m
2021-01-27 | D | 24.8 | 43.1 | Coring from 18.30 m to 43.1m, slow drilling, broken ground
| N | 24.2 | 67.3 | Coring from 43.1m to 67.3m, ground issues continue
2021-01-28 | D | 10.7 | 78 | Morning maintenance, repair cyclone, coring from 67.3m to 78m, trip for core barrel
| N | 22.1 | 100.1 | Continue coring to 100.10 m TD, rig up for logging, start logging
2021-01-29 | D | 1e-05 | 100.1 | trip out drill string, complete logging, plug hole HR20HQ-01, tear down, move to proposed hole MA-1a (HR20HQ-04), start rig up

## HR21HQ-04
Conuma Coal Hermann Mine Amendment Program - January 2021 |  |  |  |  | Good Earth Drilling
Proposed HOLE ID: | MA-1a
HOLE ID | HR20HQ-04 |  |  |  | Drill Progress
Target Depth: | 195 | Metres |  |  | 10 | no. of Shifts
Casing: | 12 | Metres |  |  | 195 | m to date
Azm : | 225 | Deg |  |  | 19.5 | m/shift (avg.)
Inclination: | -60 | Deg |  |  | -1.5385e-06 | shifts to target
Northing: | 6096749 | mN |  |  | DDH Start | 2021-01-29
Easting: | 618176 | mE |  |  | DDH Finish | 2021-02-03
Date | Shift | SHIFT | CUMULATIVE | COMMENTS
|  | Metres | Metres
2021-01-29 | D | 1e-05 | 1e-05 | Move from HR20HQ-03, rig up
| N | 32.8 | 32.8 | Complete rig up, advance casing to 12m, trip out, trip in with coring gear, coring from 12m to 32.80m
2021-01-30 | D | 27 | 59.8 | Assist with cutting casing and sealing HR20HQ-03 (2 bags benny, 2 bags cement), coring from 32.80m to 59.80m
| N | 36 | 95.8 | Coring from 59.80m to 95.80m
2021-01-31 | D | 27 | 122.8 | Coring from 95.80m to 122.80m
| N | 33 | 155.8 | Coring from 122.80m to 155.80m
2021-02-01 | D | 27 | 182.8 | Coring from 155.80m to 182.80m
| N | 12.2 | 195 | Coring from 182.80m to TD 195m, prep for logging, in pipe log, trip string out, open hole logging.
2021-02-02 | D | 1e-05 | 195 | Complete VWP install
| N | 1e-05 | 195 | Clean up site, tear down, pack up, mobe equipment to the 6km laydown for the morning move to proposed hole HA-1a

## HR21HQ-05
Conuma Coal Hermann Mine Amendment Program - January 2021 |  |  |  |  | Good Earth Drilling
Proposed HOLE ID: | HA-1a
HOLE ID | HR20HQ-05 |  |  |  | Drill Progress
Target Depth: | 75 | Metres |  |  | 7 | no. of Shifts
Casing: | 12 | Metres |  |  | 75.05 | m to date
Azm : | 210 | Deg |  |  | 10.7214 | m/shift (avg.)
Inclination: | -60 | Deg |  |  | -0.0046645 | shifts to target
Northing: | 6096152 | mN |  |  | DDH Start | 2021-02-03
Easting: | 619180 | mE |  |  | DDH Finish | 2021-02-06
Date | Shift | SHIFT | CUMULATIVE | COMMENTS
|  | Metres | Metres
2021-02-03 | D | 12 | 12 | Move equipment and crew from 6km laydown to proposed hole HA-1a, rig up, spud hole, set casing to 12m, rig up to core
| N | 11.8 | 23.8 | Late start as crew change, issues getting up to site, medic recce'd road and got stuck, showed her how to chain up, start coring from 12m to 23.80m
2021-02-04 | D | 18.05 | 41.85 | Coring from 23.80m to to 41.85m. "hard rock, slow drilling" reported by driller again
| N | 15.3 | 57.15 | Coring from 41.85m to 57.15m.
2021-02-05 | D | 7.5 | 64.65 | Coring from 57.15m to 64.65m.
| N | 10.4 | 75.05 | Coring from 64.65m to TD 75.05m, rig up for logging, log in-pipe run, trip out string
2021-02-06 | D | 1e-05 | 75.05 | Log open hole, tear down, bump rig

## HR21HQ-06
Conuma Coal Hermann Mine Amendment Program - January 2021 |  |  |  |  | Good Earth Drilling
Proposed HOLE ID: | HA-2v
HOLE ID | HR20HQ-06 |  |  |  | Drill Progress
Target Depth: | 84 | Metres |  |  | 7 | no. of Shifts
Casing: | 12 | Metres |  |  | 84.0001 | m to date
Azm : | n.a. | Deg |  |  | 12 | m/shift (avg.)
Inclination: | -90 | Deg |  |  | -9.1667e-06 | shifts to target
Northing: | 6096065 | mN |  |  | DDH Start | 2021-02-06
Easting: | 619169 | mE |  |  | DDH Finish | 2021-02-09
Date | Shift | SHIFT | CUMULATIVE | COMMENTS
|  | Metres | Metres
2021-02-06 | D | 20.75 | 20.75 | Rig up, spud HR20HQ-06, set casing to 12m, trip out odex, trip in coring gear, advance hole to 20.75m
| N | 21 | 41.75 | Coring from 20.75m to 41.75m
2021-02-07 | D | 19 | 60.75 | Coring from 41.75m to 60.75m
| N | 15 | 75.75 | Coring from 60.75m to 75.75m
2021-02-08 | D | 8.25 | 84 | Coring from 75.75m to 84m TD, issues with coring for hours (30cm), finally did a bit trip and the ID was worn out. New bit and cored to TD
| N | 1e-05 | 84 | Logging, prep for vwp install, issues with getting water
2021-02-09 | D | 0.0001 | 84.0001 | Water being pulled from east side of river now, water to rig by 1130hrs, vwp install completed by 1530hrs, tear down, move pipe truck and rig to last pad by 1930 hrs.

## HR21HQ-07
Conuma Coal Hermann Mine Amendment Program - January 2021 |  |  |  |  | Good Earth Drilling
Proposed HOLE ID: | HB-1a
HOLE ID | HR20HQ-07 |  |  |  | Drill Progress
Target Depth: | 104 | Metres |  |  | 7 | no. of Shifts
Casing: | 36 | Metres |  |  | 104.0001 | m to date
Azm : | 250 | Deg |  |  | 14.8572 | m/shift (avg.)
Inclination: | -60 | Deg |  |  | -7.4038e-06 | shifts to target
Northing: | 6096903 | mN |  |  | DDH Start | 2021-02-09
Easting: | 619060 | mE |  |  | DDH Finish | 2021-02-12
Date | Shift | SHIFT | CUMULATIVE | COMMENTS
|  | Metres | Metres
2021-02-09 | D |  | 0.0
| N | 15 | 15 | Complete move from HR20HQ-06, rig up, spud hole, advance casing to 15m.
2021-02-10 | D | 13.8 | 28.8 | set casing to 18m, rig up for coring, coring from 18m to 28.80m, water at 21m, heavily fractured/gouge and not making prgress past 28.80m, trip out coring gear, trip in odex, advance casing to 21m (water stops).
| N | 0.0001 | 28.8001 | Advance casing from 21m to 24m, standby due to -47 temp, advance from 24m and blew compressor line
2021-02-11 | D | 4.2 | 33.0001 | Rig on mechanical until afternoon, advance casing from 24m to 33m, ground heavily fractured/gouge.
| N | 21.1 | 54.1001 | Advance and set casing at 36m, rig up for coring, coring from 36m to 54.1m.
2021-02-12 | D | 49.9 | 104.0001 | Coring from 54.1m to 104m TD, rig up for logging
| N | 1e-05 | 104.0001 | Log hole, tear down, bump rig

## HR21HQ-08
Conuma Coal Hermann Mine Amendment Program - January 2021 |  |  |  |  | Good Earth Drilling
Proposed HOLE ID: | HB-2v
HOLE ID | HR20HQ-08 |  |  |  | Drill Progress
Target Depth: | 117 | Metres |  |  | 7 | no. of Shifts
Casing: | 42 | Metres |  |  | 117.0003 | m to date
Azm : | n.a. | Deg |  |  | 16.7143 | m/shift (avg.)
Inclination: | -90 | Deg |  |  | -1.7949e-05 | shifts to target
Northing: | 6096902 | mN |  |  | DDH Start | 2021-02-12
Easting: | 619065 | mE |  |  | DDH Finish | 2021-02-15
Date | Shift | SHIFT | CUMULATIVE | COMMENTS
|  | Metres | Metres
2021-02-12 | D |  | 0.0
| N | 0.0001 | 0.0001 | Rig up, trip in odex
2021-02-13 | D | 24 | 24.0001 | water truck mechanical, set casing to 24m by re-circulating water, ran out of water.
| N | 12 | 36.0001 | water truck issues continue, advance casing from 24m to 36m
2021-02-14 | D | 32.85 | 68.8501 | Repair water truck, advance and set casing at 42m, trip out odex, trip in coring gear, core from 42m to 68.85m.
| N | 48.15 | 117.0001 | Coring from 68.85m to TD 117m, rig up for logging.
2021-02-15 | D | 0.0001 | 117.0002 | Complete logging, install and grout vwp.
| N | 0.0001 | 117.0003 | Complete vwp install, tear down, pack up, mob in LD equipped pipe truck, start moving small gear to the LD pad.

## HR21RC-01
Conuma Coal Hermann Mine Amendment Program - January 2021 |  |  |  |  | Good Earth Drilling
Proposed HOLE ID: | Pilot Hole
HOLE ID | HR21RC-01 |  |  |  | Drill Progress
Target Depth: | 120 | Metres |  |  | 3 | no. of Shifts
Casing: | 9 | Metres |  |  | 122 | m to date
Azm : | n.a. | Deg |  |  | 40.6667 | m/shift (avg.)
Inclination: | -90 | Deg |  |  | -0.049181 | shifts to target
Northing: | 6096412 | mN |  |  | DDH Start | 2021-02-16
Easting: | 618858 | mE |  |  | DDH Finish | 2021-02-17
Date | Shift | SHIFT | CUMULATIVE | COMMENTS
|  | Metres | Metres
2021-02-16 | D | 42 | 42 | Move rig and equipment from HR21HQ-08 to LD pad, rig up, spud HR21RC-01, advance odex to 9m, trip in hammer assembly, advance hole to 42m.
| N | 80 | 122 | Hammer open hole from 42m to TD 122m, log in-pipe, trip out, log open hole.
2021-02-17 | D | 1e-05 | 122 | wait on logger, switch out pipe trucks, tear down, prep to bump rig

## HR21LD-01
Conuma Coal Hermann Mine Amendment Program - January 2021 |  |  |  |  | Good Earth Drilling
Proposed HOLE ID: | LDC-01
HOLE ID | HR21LD-01 |  |  |  | Drill Progress
Target Depth: | 120 | Metres |  |  | 10 | no. of Shifts
Casing: | 9 | Metres |  |  | 91.7002 | m to date
Azm : | n.a. | Deg |  |  | 9.17 | m/shift (avg.)
Inclination: | -90 | Deg |  |  | 3.0861 | shifts to target
Northing: |  | mN |  |  | DDH Start | 2021-02-17
Easting: |  | mE |  |  | DDH Finish | 2021-02-23
Date | Shift | SHIFT | CUMULATIVE | COMMENTS
|  | Metres | Metres
2021-02-17 | D | 9 | 9 | Rig up, spud hole, advance odex (12 3/4") to 9m, cement shoe, wait on cement, wait on bushings (brought two sets of 7" but not the 9" bushings).
| N | 9.7 | 18.7 | Wait on bushings, re-cement HR21HQ-01 and seal, move office laydown material to 6km laydown, hammer open hole to 18.7m
2021-02-18 | D | 18.3 | 37 | Advance open hole from 18.7m to 37m.
| N | 14 | 51 | Advance open hole from 37m to core point 51m, trip out hammer assembly, trip in coring gear, ream hole to 21.42m
2021-02-19 | D | 7 | 58 | Ream open hole from 21.42m to 51.3m, coring from 51.3m to 58m.
| N | 12.2 | 70.2 | Coring from 58.30m to 70.20m, trip in PDC to 51m to ream hole
2021-02-20 | D | 18.3 | 88.5 | Ream from 51.30m to 70.22m, PDC from 70.22m to 80.10m, coring from 80.10m to 88.52m.
| N | 3.2 | 91.7 | Coring from 88.52m to 91.72m, trip out coring gear, trip in pdc, advance open hole, ran out of water, water truck stuck, major wind/snow storm at site
2021-02-21 | D | 0.0001 | 91.7001 | Safety standby
| N | 0.0001 | 91.7002 | Safety standby
2021-02-22 | D | 0.0001 | 91.7003 | Safety standby
| N | 21.22 | 112.9203 | Warm up gear, advance open hole from 9172m to 105.22m, trip out pdc, trip in coring gear, coring from 105.22m to 112.92m.
2021-02-23 | D | 5 | 117.9203 | Coring from 112.92m to TD 117.92m, trip out coring gear, bump rig, prep site and gear for next hole

## HR21LD-02
Conuma Coal Hermann Mine Amendment Program - January 2021 |  |  |  |  | Good Earth Drilling
Proposed HOLE ID: | LDC-02
HOLE ID | HR21LD-02 |  |  |  | Drill Progress
Target Depth: | 120 | Metres |  |  | 7 | no. of Shifts
Casing: | 9 | Metres |  |  | 118.1 | m to date
Azm : | n.a. | Deg |  |  | 16.8714 | m/shift (avg.)
Inclination: | -90 | Deg |  |  | 0.11262 | shifts to target
Northing: |  | mN |  |  | DDH Start | 2021-02-23
Easting: |  | mE |  |  | DDH Finish | 2021-02-26
Date | Shift | SHIFT | CUMULATIVE | COMMENTS
|  | Metres | Metres
2021-02-23 | D |  | 0.0
| N | 9 | 9 | Complete rig up and site prep, spud hole, odex to 9m, cement casing, wait on cement
2021-02-24 | D | 22.3 | 31.3 | Drill out shoe, advance open hole from 9m to 31.3m.
| N | 23.7 | 55 | Hammer open hole from 31.30m to 55m, trip out hammer assembly, trip in coring gear, ream to 55m.
2021-02-25 | D | 15.1 | 70.1 | Coring from 55.22m to 70.12m
| N | 20.5 | 90.6 | Rig up for open hole, ream from 55m to 70m, PDC from 70m to 84.5m, core from 84.5m to 90.6m, trip in core barrel
2021-02-26 | D | 19.4 | 110 | Core from 90.60m to 91.60m, trip out, trip in PDC gear, ream from 81.50m to 91.60m, PDC from 91.60m to 104.17m, trip out, trip in coring gear, core from 104.17m to 109.97m (top of J seam 106.79m)
| N | 8.1 | 118.1 | Complete coring from 109.97m to 118.07m TD, trip out, bump rig, prep site, rig up odex for casing

## HR21LD-03
Conuma Coal Hermann Mine Amendment Program - January 2021 |  |  |  |  | Good Earth Drilling
Proposed HOLE ID: | LDC-03
HOLE ID | HR21LD-03 |  |  |  | Drill Progress
Target Depth: | 120 | Metres |  |  | 7 | no. of Shifts
Casing: | 9 | Metres |  |  | 118.7 | m to date
Azm : | n.a. | Deg |  |  | 16.9571 | m/shift (avg.)
Inclination: | -90 | Deg |  |  | 0.076664 | shifts to target
Northing: |  | mN |  |  | DDH Start | 2021-02-27
Easting: |  | mE |  |  | DDH Finish | 2021-03-02
Date | Shift | SHIFT | CUMULATIVE | COMMENTS
|  | Metres | Metres
2021-02-27 | D | 9 | 9 | Spud hole, advance casing to 9m, cement shoe, wait on cement.
| N | 17 | 26 | wait on cement, drill out shoe, open hole drilling form 9m to 26m, issues with hammer
2021-02-28 | D | 29 | 55 | repair hammer, open hole to core point 55m, trip out hammer, trip in coring gear
| N | 15.3 | 70.3 | ream from 9m to core point 55m, coring from 55.02m to 70.32m
2021-03-01 | D | 15.1 | 85.4 | Trip out coring gear, trip in PDC, ream from 30m to 70.32m, PDC from 70.32m to 80.32m, trip out PDC gear, trip in coring gear, coring from 80.32m to 85.42m.
| N | 23.9 | 109.3 | Coring from 85.42m to 91.62m, trip out, trip in and ream from 80.32m to 91.62m, open hole from 91.62m to 106.12m, trip out PDC, trip in coring gear, coring from 106.12m to 109.32m.
2021-03-02 | D | 9.4 | 118.7 | Coring from 109.32m to 118.72m TD, trip out gear, tear down, bump rig to last collar position.

## HR21LD-04
Conuma Coal Hermann Mine Amendment Program - January 2021 |  |  |  |  | Good Earth Drilling
Proposed HOLE ID: | LDC-04
HOLE ID | HR21LD-04 |  |  |  | Drill Progress
Target Depth: | 120 | Metres |  |  | 6 | no. of Shifts
Casing: | 9 | Metres |  |  | 114.9 | m to date
Azm : | n.a. | Deg |  |  | 19.15 | m/shift (avg.)
Inclination: | -90 | Deg |  |  | 0.26632 | shifts to target
Northing: |  | mN |  |  | DDH Start | 2021-03-02
Easting: |  | mE |  |  | DDH Finish | 2021-03-05
Date | Shift | SHIFT | CUMULATIVE | COMMENTS
|  | Metres | Metres
2021-03-02 | D |  | 0.0
| N | 9 | 9 | Prep site, complete rig move, spud final hole HR21LD-04, advance casing to 9m, cement casing
2021-03-03 | D | 34 | 43 | Site prep for ministry, open hole from 9m to 43m
| N | 18.1 | 61.1 | Hammer from 43m to 45m but poor penetration, trip out, trip in pdc, open hole from 45m to 55.57m, trip out, trip in coring gear reaming from 9m to 55.57m, coring from 55.57m to 61.12m.
2021-03-04 | D | 18.7 | 79.8 | Coring from 61.12m to 70.22m, trip out, trip in PDC, ream PDC from 55.57m to 70.22m, drill open hole from 70.22m to 79.80m.
| N | 26.2 | 106 | PDC from 79.80m to 85.17m, trip out, trip in coring gear, coring from 85.17m to 91.37m, trip out, trip in PDC, ream from 85.17m to 91.37m, open hole from 91.37m to 106m core point.
2021-03-05 | D | 8.9 | 114.9 | Trip out PDC, trip in coring gear, coring from 106m to 114.87m TD, commence tear down and pack up.

## Summary Collar File
Prop_ID | Collar_ID | Azi | Dip | Prop TD | Est_Casing | E_Nad83z10 | N_Nad83z10 | Start | End | Casing_m | Final_TD | Final_Easting_N83z10 | Final_Northing_N83z10 | Elevation_m | Logger_Azi | Logger_Incl
HC-1a | HR21HQ-01 | 215 | -60 | 55 | 19 | 618718 | 6097496 | 2021-01-22 | 2021-01-25 | 24 | 55 | 618718.097 | 6097497.156 | 1307.672 | 226.92 | -56.3
HC-2v | HR21HQ-02 | 0 | -90 | 61 | 20 | 618725 | 6097495 | 2021-01-25 | 2021-01-26 | 18 | 61.1 | 618724.469 | 6097495.827 | 1307.137 | n.a. | -89.3
MB-1a | HR21HQ-03 | 225 | -60 | 100 | 13 | 618297 | 6096800 | 2021-01-26 | 2021-01-29 | 9.1 | 100.1 | 618298.331 | 6096802.001 | 1406.126 | 233.46 | -59
MA-1a | HR21HQ-04 | 225 | -60 | 195 | 13 | 618176 | 6096749 | 2021-01-29 | 2021-02-03 | 12 | 195 | 618180.656 | 6096744.667 | 1432.836 | 238.66 | -60.1
HA-1a | HR21HQ-05 | 210 | -60 | 75 | 10 | 619170 | 6096059 | 2021-02-03 | 2021-02-06 | 12 | 75.05 | 619168.708 | 6096060.152 | 1605.879 | 206.56 | -59.7
HA-2v | HR21HQ-06 | 0 | -90 | 84 | 10 | 619169 | 6096065 | 2021-02-06 | 2021-02-09 | 12 | 84 | 619170.24 | 6096063.069 | 1605.964 | n.a. | -88.1
HB-1a | HR21HQ-07 | 250 | -60 | 104 | 21 | 619060 | 6096903 | 2021-02-09 | 2021-02-13 | 36 | 104 | 619063.759 | 6096901.162 | 1492.24 | 242.28 | -58.1
HB-2v | HR21HQ-08 | 0 | -90 | 117 | 19 | 619065 | 6096902 | 2021-02-13 | 2021-02-15 | 42 | 117 | 619066.047 | 6096903.647 | 1492.38 | n.a. | -88.5
BH20-3 | HR21BH-01 | n.a. | -90 | 10 | n.a. | 619029 | 6099223 | 2021-02-02 | 2021-02-02 | n.a. | 10 | 619029.639 | 6099220.634 | 1177.476
BH20-4 | HR21BH-02 | n.a. | -90 | 10 | n.a. | 619060 | 6099174 | 2021-02-02 | 2021-02-02 | n.a. | 10 | 619060.838 | 6099173.799 | 1179.245
BH20-5 | HR21BH-03 | n.a. | -90 | 10 | n.a. | 619084 | 6099158 | 2021-02-02 | 2021-02-03 | n.a. | 11.5 | 619083.725 | 6099158.192 | 1179.624
BH20-6 | HR21BH-04 | n.a. | -90 | 10 | n.a. | 619101 | 6099136 | 2021-02-03 | 2021-02-03 | n.a. | 10 | 619101.408 | 6099133.137 | 1180.047
BH20-1 | HR21BH-05 | n.a. | -90 | 8 | n.a. | 619084 | 6098633 | 2021-02-03 | 2021-02-04 | n.a. | 8.5 | 619086.536 | 6098636.246 | 1192.684
BH20-2 | HR21BH-06 | n.a. | -90 | 8 | n.a. | 619071 | 6098735 | 2021-02-04 | 2021-02-04 | n.a. | 8.5 | 619073.189 | 6098736.312 | 1186.481
BH20-11 | HR21BH-07 | n.a. | -90 | 8 | n.a. | 618964 | 6098022 | 2021-02-04 | 2021-02-04 | n.a. | 6 | 618963.798 | 6098021.58 | 1274.315
BH20-12 | HR21BH-08 | n.a. | -90 | 8 | n.a. | 618722 | 6097985 | 2021-02-05 | 2021-02-05 | n.a. | 2.4 | 618724.133 | 6097983.202 | 1268.775
BH20-9 | HR21BH-09 | n.a. | -90 | 8 | n.a. | 618632 | 6098181 | 2021-02-06 | 2021-02-06 | n.a. | 8.8 | 618634.35 | 6098178.077 | 1229.61
BH20-10 | HR21BH-10 | n.a. | -90 | 8 | n.a. | 618762 | 6098254 | 2021-02-06 | 2021-02-06 | n.a. | 7.6 | 618765.869 | 6098256.762 | 1217.24
BH20-7 | HR21BH-11 | n.a. | -90 | 8 | n.a. | 618751 | 6099307 | 2021-02-06 | 2021-02-06 | n.a. | 8.8 | 618753.101 | 6099303.63 | 1185.494
BH20-8 |  | n.a. | -90 | 8 | n.a. | 618770 | 6099213 | CANCELLED
Pilot Hole | HR21RC-01 | n.a. | -90 | 120 | 10 | 618858 | 6096412 | 2021-02-16 | 2021-02-17 | 9 | 122 | 618865.376 | 6096417.607 | 1518.769 | n.a. | -88.2
LDC-01 | HR21LD-01 | n.a. | -90 | 120 | 10 |  |  | 2021-02-17 | 2021-02-23 | 9 | 117.92 | 618864.689 | 6096419.481 | 1519.224
LDC-02 | HR21LD-02 | n.a. | -90 | 120 | 10 |  |  | 2021-02-23 | 2021-02-26 | 9 | 118.07
LDC-03 | HR21LD-03 | n.a. | -90 | 120 | 10 |  |  | 2021-02-27 | 2021-03-02 | 9 | 118.72
LDC-04 | HR21LD-04 | n.a. | -90 | 120 | 10 |  |  | 2021-03-02 | 2021-03-05 | 9 | 114.87

## Collar Surveys
Hole_ID | Easting_N83z10 | Northing_N83z10 | Elevation_m
HR21HQ-01 | 618718.097 | 6097497.156 | 1307.672
HR21HQ-02 | 618724.469 | 6097495.827 | 1307.137
HR21HQ-03 | 618298.331 | 6096802.001 | 1406.126
HR21HQ-04 | 618180.656 | 6096744.667 | 1432.836
HR21HQ-05 | 619168.708 | 6096060.152 | 1605.879
HR21HQ-06 | 619170.24 | 6096063.069 | 1605.964
HR21HQ-07 | 619063.759 | 6096901.162 | 1492.24
HR21HQ-08 | 619066.047 | 6096903.647 | 1492.38
HR21BH-01 | 619029.639 | 6099220.634 | 1177.476
HR21BH-02 | 619060.838 | 6099173.799 | 1179.245
HR21BH-03 | 619083.725 | 6099158.192 | 1179.624
HR21BH-04 | 619101.408 | 6099133.137 | 1180.047
HR21BH-05 | 619086.536 | 6098636.246 | 1192.684
HR21BH-06 | 619073.189 | 6098736.312 | 1186.481
HR21BH-07 | 618963.798 | 6098021.58 | 1274.315
HR21BH-08 | 618724.133 | 6097983.202 | 1268.775
HR21BH-09 | 618634.35 | 6098178.077 | 1229.61
HR21BH-10 | 618765.869 | 6098256.762 | 1217.24
HR21BH-11 | 618753.101 | 6099303.63 | 1185.494
HR21RC-01 | 618865.376 | 6096417.607 | 1518.769
HR21LD-01 | 618864.689 | 6096419.481 | 1519.224
HR14-04C | 618857.7 | 6096419 | 1000
HR14-04AC | 618857 | 6096425 | 1000

## Proposed Holes
DR-1 Hermann Geotechnical Coring Program
Location | Easting | Northing | Elevation | Tenure | Azimuth | Dip | Depth | Casing | Rockhead | Predictions | Shifts
HA-1a | 619180 | 6096152 |  | 383183 | 210 | -60 | 75 | 10 | 0.3 | Start in Hulcross, basal grit @ 60m, Notikewin @ 60.2m | 4
HA-2v | 619180 | 6096152 |  | 383183 | 0 | -90 | 84 | 10 | 0.2 | Start in Hulcross, basal grit @ 69m, Notikewin @ 69.2m | 4
HB-1a | 619053 | 6096895 |  | 383181 | 250 | -60 | 104 | 21 | 11 | Start in Hulcross, Ash-16 @ 15m, faults possible to probable @ 18-32m, expect broken ground, Ash-13 @ 33.5m, basal grit @ 88.5m, Notikewin @ 89m | 5
HB-2v | 619053 | 6096895 |  | 383181 | 0 | -90 | 117 | 19 | 9 | Start in Hulcross, Ash-16 @ 17m, faults possible to probable @ 21-37m, expect broken ground, Ash-13 @ 38.5m, basal grit @ 101.8m, Notikewin @ 102.2m | 5
HC-1a | 618680 | 6097524 |  | 383181 | 215 | -60 | 55 | 19 | 9 | Start in Hulcross above Ash-05, basal grit @ 40m, Notikewin @ 40.3m | 3
HC-2v | 618680 | 6097524 |  | 383181 | 0 | -90 | 61 | 20 | 10 | Start in Hulcross above Ash-05, basal grit @ 46m, Notikewin @ 46.4m | 3
MA-1a | 618178 | 6096762 |  | 383182 | 225 | -60 | 195 | 13 | 3 | Start in Spieker, Cowmoose @ 90m, Green Marker @ 180m, Chamberlain @ 180.5m | 8
MB-1a | 618334 | 6096840 |  | 383181 | 225 | -60 | 100 | 13 | 3 | Start in Upper Quintette, Medial Siltstone @ 25m, L-Ash @ 40m, Lower Quintette @ 43m, Spieker @ 75m | 4
[7 empty] | 791 | 125 |  |  | 36
DR-2 Borehole Program
Location | Easting | Northing | Prop_TD_m | Final_TD_m | Azimuth | Dip | Depth | Install
BH20-1 | 619082 | 6098628 | 8 |  | n.a. | -90 | 8 | Y
BH20-2 | 619078 | 6098745 | 8 |  | n.a. | -90 | 8 | Y
BH20-3 | 619033 | 6099227 | 10 |  | n.a. | -90 | 10 | N
BH20-4 | 619071 | 6099207 | 10 |  | n.a. | -90 | 10 | N
BH20-5 | 619109 | 6099187 | 10 |  | n.a. | -90 | 10 | N
BH20-6 | 619102 | 6099131 | 10 |  | n.a. | -90 | 10 | N
BH20-7 | 618731 | 6099300 | 8 |  | n.a. | -90 | 10 | N
BH20-8 | 618770 | 6099213 | 8 |  | n.a. | -90 | 10 | N
BH20-9 | 618644 | 6098219 | 8 |  | n.a. | -90 | 10 | N
BH20-10 | 618787 | 6098249 | 8 |  | n.a. | -90 | 10 | N
BH20-11 | 618967 | 6098016 | 8 |  | n.a. | -90 | 10 | N
BH20-12 | 618731 | 6097980 | 8 |  | n.a. | -90 | 10 | N
DR-3 LD Program
Location | Easting | Northing | Elevation | Tenure | Azimuth | Dip | Depth | Casing
Pilot Hole | 618858 | 6096412 |  |  | n.a. | -90 | 120 | 10